## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KHARI GERYA AND ITS ADJOINING MOUZAS PWSS | SM/18532 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHARI GERYA AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000361/2023-2024 | 1689/W/MMD | 04/08/2023 | 31/01/2024 | ORIENTAL ENGINEERING CO. | 25.25 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KHARI GERYA AND ITS ADJOINING MOUZAS PWSS | SM/18532 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 400 Cum (Intze type with Pile Foundation) OHR & Accommodate FHTC (2,792 Nos.) including 02(Two) years O&M under JJM with allied work for Khari Gerya & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000385/2023-2024 | 5059/MD | 26/10/2023 | 25/09/2025 | M/S. CARE | 871.34 | 299.18 | 34.33 | 35
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KHARI GERYA AND ITS ADJOINING MOUZAS PWSS | SM/18532 | New | Material Requisition To Resource Division |  |  | RTOR000255/2023-2024 | 1589/MD | 15/05/2023 | 15/05/2023 | Resource Division | 34.55 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KHARI GERYA AND ITS ADJOINING MOUZAS PWSS | SM/18532 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002834/2023-2024 | 339/MMSD-I | 05/03/2024 | 05/01/2025 | M/S BIKASH DE | 6.3 | 0.14 | 2.17 | 50
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KHARI GERYA AND ITS ADJOINING MOUZAS PWSS | SM/18532 | New | Continuation work order for Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. (Vehicle No. WB 33 C 6546) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002164/2024-2025 | 1826/MMSD-I | 30/12/2024 | 29/06/2025 | M/S BIKASH DE | 3.69 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KHARI GERYA AND ITS ADJOINING MOUZAS PWSS | SM/18532 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of KHARIGERIA PWSS. REF CONSUMER ID-204212338, APPLICATION NO-2004593715, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/03745/2023-2024 | BP-2023-24-685 | 16/02/2024 | 16/02/2024 | WBSEDCL | 4.92 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KHARI GERYA AND ITS ADJOINING MOUZAS PWSS | SM/18532 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of KHARIGERIA PWSS. REF CONSUMER ID-204211927, APPLICATION NO-2004590188 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/03744/2023-2024 | BP-2023-24-686 | 16/02/2024 | 16/02/2024 | WBSEDCL | 3.82 | 0 | 0 | 0
Total | [13 empty] | 949.87 | 299.31 | 31.51