## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | DUBRAJI AND ITS ADJOINING MOUZAS PWSS | SM/18533 | New | Material Requisition To Resource Division |  |  | RTOR000101/2022-2023 | 178/MD | 16/01/2023 | 16/01/2023 | Resource Division | 23.7 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | DUBRAJI AND ITS ADJOINING MOUZAS PWSS | SM/18533 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DUBRAJI AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000364/2023-2024 | 1692/W/MMD | 04/08/2023 | 31/01/2024 | A.S.ENTERPRISE | 27.34 | 18.45 | 67.47 | 40
3 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | DUBRAJI AND ITS ADJOINING MOUZAS PWSS | SM/18533 | New | Material Requisition To Resource Division |  |  | RTOR000086/2024-2025 | 3488/MD | 25/11/2024 | 25/11/2024 | Resource Division | 18.82 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | DUBRAJI AND ITS ADJOINING MOUZAS PWSS | SM/18533 | New | Quotation for new power connection at Dubraji PWSS P/H- II , application no - 2004609001 , Ref id - 204222611 |  |  | BILL/04198/2023-2024 | BP-2023-24-778 | 06/03/2024 | 06/03/2024 | WBSEDCL | 6.46 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | DUBRAJI AND ITS ADJOINING MOUZAS PWSS | SM/18533 | New | Quotation for new power connection at Dubraji PWSS P/H- I , application no - 2004608941 , Ref id - 204222615 |  |  | BILL/04196/2023-2024 | BP-2023-24-777 | 06/03/2024 | 06/03/2024 | WBSEDCL | 1.81 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | DUBRAJI AND ITS ADJOINING MOUZAS PWSS | SM/18533 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 Cum OHR (Intze type with Pile Foundation) & Accommodate FHTC (3,056 nos.) under JJM with allied work including 02 (Two ) Years Operation & Maintenance for Dubraji & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000271/2023-2024 | 3258/MD | 12/09/2023 | 01/09/2025 | TAPAS SANTRA | 927.59 | 514.73 | 55.49 | 75
7 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | DUBRAJI AND ITS ADJOINING MOUZAS PWSS | SM/18533 | New | Route survey & way leave permission along & across of National Highway in Dubraji PWSS under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000505/2024-2025 | 588/MD | 03/03/2025 | 24/03/2025 | DONA ASSOCIATES | 10.21 | 0 | 0 | 0
Total | [13 empty] | 1015.94 | 533.17 | 52.48