## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | GHOSHPUR PIPED WATER SUPPLY SCHEME | SM/18535 | New | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 79/MD | 09/01/2023 | 09/01/2023 | Resource Division | 16.2 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | GHOSHPUR PIPED WATER SUPPLY SCHEME | SM/18535 | New | Material Requisition To Resource Division |  |  | RTOR000066/2024-2025 | 3386/MD | 25/11/2024 | 25/11/2024 | Resource Division | 20.73 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | GHOSHPUR PIPED WATER SUPPLY SCHEME | SM/18535 | New | ELECTRIC QUOTATION BILL FOR TW NO-II OF GHOSHPUR PWSS. REF CONSUMER ID-204294953, APPLICATION NO-2004713752, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/01789/2024-2025 | C072449541730 | 02/08/2024 | 02/08/2024 | WBSEDCL | 3.55 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | GHOSHPUR PIPED WATER SUPPLY SCHEME | SM/18535 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of GHOSHPUR PWSS. REF CONSUMER ID-204218492, APPLICATION NO-2004603166, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/03779/2023-2024 | BP-2023-24-713 | 20/02/2024 | 20/02/2024 | WBSEDCL | 4.85 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | GHOSHPUR PIPED WATER SUPPLY SCHEME | SM/18535 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 500 cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,366 nos.) under JJM with allied work for Ghoshpur PWSS in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000280/2023-2024 | 3842/MD | 21/09/2023 | 12/06/2026 | M/S. A.R. ENTERPRISE. | 917.44 | 135.65 | 14.79 | 35
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | GHOSHPUR PIPED WATER SUPPLY SCHEME | SM/18535 | New | Laying of rising main & interconnection for Ghoshpur & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 650 Mtr.) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000388/2024-2025 | 60/MD | 07/01/2025 | 21/02/2025 | A-PLUS | 6.5 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | GHOSHPUR PIPED WATER SUPPLY SCHEME | SM/18535 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different ongoing piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.- w.e.f.-01-07-2025 to 28-02-2026 (Vehicle No. WB33C 6546) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000513/2025-2026 | 842/MMSD-I | 11/06/2025 | 09/02/2026 | M/S BIKASH DE | 3.66 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | GHOSHPUR PIPED WATER SUPPLY SCHEME | SM/18535 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GHOSHPUR PIPED WATER SUPPLY SCHEMEunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000351/2023-2024 | 1686/W/MMD | 04/08/2023 | 12/06/2025 | SHOVAN KUMAR DAS | 27.39 | 19.55 | 71.38 | 20
Total | [13 empty] | 1000.33 | 155.2 | 15.51