## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Bhuta (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. | SM/18539 | New | Material Requisition To Resource Division |  |  | RTOR000241/2023-2024 | 1523/MD | 12/05/2023 | 12/05/2023 | Resource Division | 59.93 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Bhuta (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. | SM/18539 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Bhuta (Zone-I and II) and its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000365/2023-2024 | 1695/W/MMD | 04/08/2023 | 31/01/2024 | AMUSAR IMPEX PVT. LTD | 45.31 | 35.64 | 78.66 | 50
3 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Bhuta (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. | SM/18539 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Bhutna & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000093/2022-2023 | 673/MD | 11/04/2022 | 01/05/2022 | GOBINDA MAITY | 8.37 | 6.81 | 81.35 | 100
4 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Bhuta (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. | SM/18539 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, 350 Cum & 250 cum OHR (Zone- I & II) (Intze type with pile foundation) & Accommodate FHTC (3,339 Nos.) including Two years O&M under JJM with allied work for Bhuta (Zone- I & Zone-II) & its adjoining mouzas W/S Scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000392/2023-2024 | 5066/MD | 26/10/2023 | 10/07/2026 | M/S. SOURABH KUMAR ROY | 838.26 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Bhuta (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. | SM/18539 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 05/01/2025 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Bhuta (Zone-I & II) & its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. | SM/18539 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002214/2024-2025 | 432/MMSD-I | 26/03/2025 | 23/09/2025 | S.K.ENTERPRISE | 4.11 | 0 | 0 | 0
Total | [13 empty] | 962.28 | 42.45 | 4.41