## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18540 | New | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Tatarpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000750/2022-2023 | 1269/MD | 23/06/2022 | 03/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.39 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18540 | New | Material Requisition To Resource Division |  |  | RTOR000151/2022-2023 | 534/MD | 21/02/2023 | 21/02/2023 | Resource Division | 239.55 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18540 | New | Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 700 cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,529 nos.) under JJM with allied work for Tatarpur PWSS in Daspur -I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000828/2023-2024 | 741/MD | 13/03/2024 | 09/03/2025 | KHAN ENTERPRISE | 820.87 | 0 | 0 | 35
4 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18540 | New | Sinking of Three nos. 250 X 150 mm dia. X 200 mtr. Depth deep tube well by direct rotary method under JJM with allied work for Tatarpur PWSS in Daspur-I block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000184/2023-2024 | 2737/MD | 01/08/2023 | 31/08/2023 | SAJAL JANA | 35.06 | 0 | 0 | 100
5 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18540 | New | QUOTATION MONEY FOR TATARPUR WATER SUPPLY SCHEME, T W - II, JJM WORKS, SCHEME CODE SM/18540, APPLICATION NO 2004696073, REFERENCE ID 204284332, DASPUR CCC, WBSEDCL |  |  | BILL/00642/2024-2025 | BP-2024-25-122 | 06/05/2024 | 06/05/2024 | WBSEDCL | 3.49 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18540 | New | QUOTATION MONEY FOR TATARPUR WATER SUPPLY SCHEME, T W - III , JJM WORKS, SCHEME CODE SM/18540, APPLICATION NO 2004696081, REFERENCE ID 2204284306, DASPUR CCC, WBSEDCL |  |  | BILL/00644/2024-2025 | BP-2024-25-121 | 06/05/2024 | 06/05/2024 | WBSEDCL | 4.33 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18540 | New | QUOTATION MONEY FOR TATARPUR WATER SUPPLY SCHEME, T W - I, JJM WORKS, SCHEME CODE SM/18540, APPLICATION NO 2004700117, REFERENCE ID 204286354, DASPUR CCC, WBSEDCL |  |  | BILL/00828/2024-2025 | BP-2024-25-159 | 13/05/2024 | 13/05/2024 | WBSEDCL | 7.37 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18540 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER DASPUR - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTEunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000368/2023-2024 | 1694/W/MMD | 04/08/2023 | 01/09/2025 | A G ENTERPRISE | 78.38 | 0 | 0 | 20
9 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Tatarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18540 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002724/2023-2024 | 1069/W/MMD | 14/03/2024 | 10/09/2024 | SWAPAN BANERJEE | 10.42 | 0 | 0 | 100
Total | [13 empty] | 1201.87 | 0 | 0