## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | JAGANATH CHAK AND ITS ADJOINING MOUZAS PWSS | SM/18583 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for JAGANATH CHAK AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000384/2023-2024 | 1723/W/MMD | 09/08/2023 | 05/02/2024 | S.K.ENTERPRISE | 25.26 | 19.8 | 78.38 | 50
2 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | JAGANATH CHAK AND ITS ADJOINING MOUZAS PWSS | SM/18583 | New | Sinking of Tube wells, Construction of 400 CuM Capacity R.C.C Over Head Reservoirs (Over Raft / Pile Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (6,875 Nos.) for Jagannathchak & Barbasi Pipe W/S Scheme including 2 years O&M within Kharagpur-II Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE3 Kharagpur Sub-division | ORD/000248/2023-2024 | 3101/MD | 25/08/2023 | 03/05/2026 | GOBINDA MAITY | 1932.69 | 494.48 | 25.59 | 25
3 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | JAGANATH CHAK AND ITS ADJOINING MOUZAS PWSS | SM/18583 | New | Material Requisition To Resource Division |  |  | RTOR000242/2023-2024 | 1529/MD | 12/05/2023 | 12/05/2023 | Resource Division | 308.47 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | JAGANATH CHAK AND ITS ADJOINING MOUZAS PWSS | SM/18583 | New | Quotation for new power connection at Jaganathchak T/W - I Within Khargpur - II Block, Application No - 2004975165 , Ref ID - 204452539 |  |  | BILL/03157/2024-2025 | C122403005259 | 03/12/2024 | 03/12/2024 | WBSEDCL | 5.31 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | JAGANATH CHAK AND ITS ADJOINING MOUZAS PWSS | SM/18583 | New | Quotation for new power connection at Jaganathchak T/W - II Within Khargpur - II Block, Application No - 2004975111 , Ref ID - 204452538 |  |  | BILL/03156/2024-2025 | C122403006019 | 03/12/2024 | 03/12/2024 | WBSEDCL | 3.56 | 0 | 0 | 0
Total | [13 empty] | 2275.29 | 514.28 | 22.6