## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | AMLA BANI AND ITS ADJOINING MOUZAS PWSS | SM/18584 | New | Material Requisition To Resource Division |  |  | RTOR000053/2022-2023 | 61/MD | 09/01/2023 | 09/01/2023 | Resource Division | 16.89 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | AMLA BANI AND ITS ADJOINING MOUZAS PWSS | SM/18584 | New | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001826/2023-2024 | 1685/MMSD-I | 19/12/2023 | 17/02/2024 | M/S BIKASH DE | 0.29 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | AMLA BANI AND ITS ADJOINING MOUZAS PWSS | SM/18584 | New | Fuel for Inspection Vehicle of covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission Program. [w.e.f. 01-01-2024 to 29-02-2024] | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002853/2023-2024 | 1698/MMSD-I | 19/12/2023 | 17/02/2024 | M/S BIKASH DE | 0.83 | 0 | 0 | 100
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | AMLA BANI AND ITS ADJOINING MOUZAS PWSS | SM/18584 | New | Material Requisition To Resource Division |  |  | RTOR000056/2024-2025 | 3376/MD | 25/11/2024 | 25/11/2024 | Resource Division | 14.49 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | AMLA BANI AND ITS ADJOINING MOUZAS PWSS | SM/18584 | New | Electric quotation bill for Tw No-II of Amla Bani PWSS. (Ref Consumer ID-204182328) |  |  | BILL/03336/2023-2024 | BP-2023-24-559 | 16/01/2024 | 16/01/2024 | WBSEDCL | 2.93 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | AMLA BANI AND ITS ADJOINING MOUZAS PWSS | SM/18584 | New | Electric quotation bill for Tw No-I of Amla Bani PWSS (Ref Consumer ID-204182336) |  |  | BILL/03335/2023-2024 | BP-2023-24-560 | 16/01/2024 | 16/01/2024 | WBSEDCL | 5.76 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | AMLA BANI AND ITS ADJOINING MOUZAS PWSS | SM/18584 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AMLA BANI AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000385/2023-2024 | 1724/W/MMD | 09/08/2023 | 31/03/2025 | K.S.P. ENTERPRISE | 25.24 | 18.02 | 71.39 | 20
8 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | AMLA BANI AND ITS ADJOINING MOUZAS PWSS | SM/18584 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 350 cum OHR (Intze type with raft foundation) & Accommodate FHTC (2,353 nos.) under JJM with allied work for Amlabani PWSS in Keshpur Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000281/2023-2024 | 3843/MD | 21/09/2023 | 12/06/2026 | M/S. A.R. ENTERPRISE. | 1033.27 | 651.73 | 63.07 | 43
9 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | AMLA BANI AND ITS ADJOINING MOUZAS PWSS | SM/18584 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002834/2023-2024 | 339/MMSD-I | 05/03/2024 | 05/01/2025 | M/S BIKASH DE | 6.3 | 0.54 | 8.51 | 50
Total | [13 empty] | 1106.01 | 670.29 | 60.6