## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/18585 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Shila Rajnagar & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000653/2022-2023 | 1751/MD | 24/08/2022 | 13/09/2022 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.97 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/18585 | New | Material Requisition To Resource Division |  |  | RTOR000063/2022-2023 | 71/MD | 09/01/2023 | 09/01/2023 | Resource Division | 15.92 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/18585 | New | Material Requisition To Resource Division |  |  | RTOR000038/2024-2025 | 3365/MD | 25/11/2024 | 25/11/2024 | Resource Division | 17.22 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/18585 | New | QUOTATION MONEY FOR SHILARAJNAGAR WATER SUPPLY SCHEME, T W NO 2, JJM WORKS, SCHEME CODE SM/18585, APPLICATION NO 2004628032, REFERENCE ID 204234631, GHATAL CCC, WBSEDCL |  |  | BILL/04401/2023-2024 | BP-2023-24-840 | 14/03/2024 | 14/03/2024 | WBSEDCL | 3.29 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/18585 | New | QUOTATION MONEY FOR SHILARAJNAGAR WATER SUPPLY SCHEME, T W NO 1, JJM WORKS, SCHEME CODE SM/18585, APPLICATION NO 2004627434, REFERENCE ID 204234630, GHATAL CCC, WBSEDCL |  |  | BILL/04402/2023-2024 | BP-2023-24-841 | 14/03/2024 | 14/03/2024 | WBSEDCL | 4.46 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/18585 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000391/2023-2024 | 1730/W/MMD | 09/08/2023 | 01/03/2025 | ORIENTAL ENGINEERING CO. | 27.35 | 0 | 0 | 55
7 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/18585 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House , Boundary Wall, Soil investigation, 450 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,796 nos.) under JJM with allied work for Shilarajnagar PWSS in Ghatal Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE2 Ghatal Sub-division | ORD/000249/2023-2024 | 3102/MD | 25/08/2023 | 10/02/2026 | DIPAK KUMAR BAKLY | 884.14 | 0 | 0 | 5
8 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/18585 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002214/2024-2025 | 432/MMSD-I | 26/03/2025 | 23/09/2025 | S.K.ENTERPRISE | 4.11 | 0 | 0 | 0
Total | [13 empty] | 963.47 | 0 | 0