## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Makarampur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18586 | New | Material Requisition To Resource Division |  |  | RTOR000049/2022-2023 | 108/MD | 10/01/2023 | 10/01/2023 | Resource Division | 103.9 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Makarampur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18586 | New | Material Requisition To Resource Division |  |  | RTOR000016/2024-2025 | 3337/MD | 25/11/2024 | 25/11/2024 | Resource Division | 14.38 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Makarampur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18586 | New | QUOTATION MONEY FOR MAKARAMPUR WATER SUPPLY SCHEME , T W - II , JJM WORKS, SCHEME CODE SM/18586, APPLICATION NO 2004696147, REFERENCE ID 204284316, DASPUR CCC, WBSEDCL |  |  | BILL/00637/2024-2025 | BP-2024-25-118 | 06/05/2024 | 06/05/2024 | WBSEDCL | 3.55 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Makarampur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18586 | New | QUOTATION MONEY FOR MAKARAMPUR WATER SUPPLY SCHEME , T W - I , JJM WORKS, SCHEME CODE SM/18586, APPLICATION NO 2004696153, REFERENCE ID 204284318, DASPUR CCC, WBSEDCL |  |  | BILL/00636/2024-2025 | BP-2024-25-119 | 06/05/2024 | 06/05/2024 | WBSEDCL | 5.84 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Makarampur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18586 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Makarampur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000382/2023-2024 | 1721/W/MMD | 09/08/2023 | 01/09/2025 | S.G.TECHNICAL SERVICE | 23 | 0 | 0 | 85
6 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Makarampur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/18586 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 450 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,335 nos.) under JJM with allied work for Makarampur PWSS in Daspur- I Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance Charge within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000397/2023-2024 | 5090/MD | 30/10/2023 | 23/12/2025 | SWACH ENVIRONMENT PRIVATE LIMITED | 733.83 | 0 | 0 | 55
Total | [13 empty] | 884.5 | 0 | 0