## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | MELERACHAK AND ITS ADJOINING MOUZAS PWSS | SM/18587 | New | Material Requisition To Resource Division |  |  | RTOR000102/2022-2023 | 179/MD | 16/01/2023 | 16/01/2023 | Resource Division | 16.2 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | MELERACHAK AND ITS ADJOINING MOUZAS PWSS | SM/18587 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MELERACHAK AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division | ORD/000390/2023-2024 | 1729/W/MMD | 09/08/2023 | 05/02/2024 | SUJOY RANJAN BHOWMICK | 27.36 | 0 | 0 | 60
3 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | MELERACHAK AND ITS ADJOINING MOUZAS PWSS | SM/18587 | New | Material Requisition To Resource Division |  |  | RTOR000087/2024-2025 | 3439/MD | 25/11/2024 | 25/11/2024 | Resource Division | 21.97 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | MELERACHAK AND ITS ADJOINING MOUZAS PWSS | SM/18587 | New | Quotation for new power connection at Melerachak water supply scheme T/W - I |  |  | BILL/03559/2023-2024 | BP-2023-24-630 | 08/02/2024 | 08/02/2024 | WBSEDCL | 4.37 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | MELERACHAK AND ITS ADJOINING MOUZAS PWSS | SM/18587 | New | Quotation for new power connection at Melerachak PWSS , T/W - I , Application no - 2004582161 , Ref ID - 204206275 , Madpur CCC |  |  | BILL/03748/2023-2024 | BP-2023-24-706 | 16/02/2024 | 16/02/2024 | WBSEDCL | 4.25 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | MELERACHAK AND ITS ADJOINING MOUZAS PWSS | SM/18587 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 500 Cum OHR (Intze type with Pile foundation) & Accommodate FHTC (3,567 nos.) under JJM with allied work including 02 (Tow) Years Operation & Maintenance for Melerchak PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE3 Kharagpur Sub-division | ORD/000274/2023-2024 | 3275/MD | 13/09/2023 | 02/09/2025 | TAPAS SANTRA | 973.12 | 0 | 0 | 73
Total | [13 empty] | 1047.28 | 0 | 0