## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANGRUL TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18615 | New | Material Requisition To Resource Division |  |  | RTOR000285/2023-2024 | 4056/MD | 12/10/2023 | 12/10/2023 | Resource Division | 46.13 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Mechanical | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANGRUL TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18615 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at MANGRUL Water supply scheme, Chandrakona -I block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000753/2023-2024 | 2283/W/MMD | 29/08/2023 | 25/02/2024 | S.B.ENTERPRISE | 30.52 | 0 | 0 | 90
3 | PASCHIM MEDINIPUR | Chandrakona-I | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANGRUL TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18615 | New | Quotation for Mangrul T/W - 2 water supply scheme. |  |  | BILL/01407/2023-2024 | 67/JMD | 13/03/2024 | 13/03/2024 | WBSEDCL | 2.79 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Chandrakona-I | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANGRUL TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18615 | New | Aditional quotation of new service connection at Mangrul T/W-I due to way leave problem under Ramjibanpur C.C.C. |  |  | BILL/00817/2024-2025 | 296/JMD | 09/08/2024 | 09/08/2024 | WBSEDCL | 0.49 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Chandrakona-I | Jhargram Mechanical Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANGRUL TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18615 | New | New Service connection charges. |  |  | BILL/01470/2023-2024 | 79/JMD | 20/03/2024 | 20/03/2024 | WBSEDCL | 3.69 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANGRUL TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18615 | New | Sinking of Tube wells, Construction of 450 CuM Capacity R.C.C Over Head Reservoirs (Over Pile Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (6507) for Bagchhari & Mangrul Pipe W/S Scheme including Two years O&M within Chandrakona-I Block under Ghatal Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000209/2023-2024 | 2825/MD | 07/08/2023 | 28/09/2025 | GOBINDA MAITY | 1766.48 | 0 | 0 | 70
7 | PASCHIM MEDINIPUR | Chandrakona-I | Midnapore Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANGRUL TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. | SM/18615 | New | Laying of rising main & additional distribution pipe line due to re-design of mouzas Pipe W/S Schemes [Mangrul / Ramkrishnapur / Bagchhari / Purshuri] at Chandrakona-I block under Ghatal Sub-Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000380/2024-2025 | 55/MD | 07/01/2025 | 30/09/2025 | GOBINDA MAITY | 79.62 | 0 | 0 | 60
Total | [13 empty] | 1929.72 | 0 | 0