## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | SM/18620 | New | Construction of Pump House, Boundary wall & Accommodate FHTC (842 nos.) under JJM in (Zone-I) for Proposed Mohar-Katina (Zone-I & II) PWSS in Sabang Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-E] | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000189/2023-2024 | 2803/MD | 07/08/2023 | 06/10/2023 | SHAKEEL KHAN | 64.42 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | SM/18620 | New | Construction of Pump House, Boundary wall & Accommodate FHTC (568 nos.) under JJM with allied work for Mohar-Katina (Zone-II) PWSS in Sabang block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-F] | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000192/2023-2024 | 2806/MD | 07/08/2023 | 06/10/2023 | NUTAN BAZAR ENGINEER,S CO-OPERATIVE SOCIETY LTD. | 48.67 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | SM/18620 | New | Laying distribution pipe line & Accommodate FHTC (200 nos.) under JJM with allied work for Proposed Mohar-Katina (Zone-II) PWSS in Sabang. Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000241/2023-2024 | 3051/MD | 23/08/2023 | 22/09/2023 | JOY GURU TRADING | 33.64 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | SM/18620 | New | Material Requisition To Resource Division |  |  | RTOR000080/2022-2023 | 199/MD | 16/01/2023 | 16/01/2023 | Resource Division | 45.97 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | SM/18620 | New | Laying distribution pipe line & Accommodate FHTC (400 nos.) under JJM with allied work for Proposed Mohar-Katina (Zone-II) PWSS in Sabang Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000190/2023-2024 | 2804/MD | 07/08/2023 | 28/11/2025 | SANKAR PRASAD MAITY | 64.97 | 0.89 | 1.37 | 40
6 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | SM/18620 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000387/2023-2024 | 1726/W/MMD | 09/08/2023 | 05/02/2024 | DAS ENTERPRISE | 47.42 | 31.08 | 65.55 | 30
7 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | SM/18620 | New | Laying of Distribution Pipe Line and FHTC (1182 nos.) work including 2 (Two) years O&M for Proposed Mohar-Katina & its adjoining Mouzas (Zone-I) PWSS, Block- Sabong, Dist: - Paschim Medinipur under Midnapore Division, PHE Dte. [PART-D] | AE/RWS Midnapore Sub Division |  | ORD/000030/2024-2025 | 2119/MD | 09/07/2024 | 07/09/2024 | BHUWALKA DEVELOPMENTS PRIVATE LIMITED | 228.56 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | SM/18620 | New | Sinking of 2 (Two) nos. 250 X 150 X 170 mtr. depth deep Tube well (Zone-I) for Proposed Mohar- Katina & its adjoining mouzas PWSS, Block- Sabong, Dist:- Paschim Medinipur under Midnapur Division, PHE Dte. [PART-A] | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000188/2023-2024 | 2802/MD | 07/08/2023 | 28/08/2023 | MANISHIKA CONSTRUCTION | 16.89 | 16.86 | 99.84 | 50
9 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | SM/18620 | New | Sinking of 2 (Two) Nos. 200 X 100 X 170 mtr. depth deep Tube well (Zone-II) for Proposed Mohar-Katina & its adjoining mouzas (Zone-I & II) PWSS, Block- Sabong Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-E] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000187/2023-2024 | 2801/MD | 07/08/2023 | 28/08/2023 | MANNA COMPUTER | 13.54 | 12.99 | 95.98 | 100
10 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | SM/18620 | New | QUOTATION MONEY FOR MOHAR-KATINA WATER SUPPLY SCHEME, T W NO I, [ KATINA] , JJM WORKS, SCHEME CODE SM/18620, APPLICATION NO 2004806819, REFERENCE ID 204348010, SABANG CCC, WBSEDCL |  |  | BILL/01459/2024-2025 | BP-2024-25-422 | 15/07/2024 | 15/07/2024 | WBSEDCL | 6.29 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | SM/18620 | New | QUOTATION MONEY FOR MOHAR-KATINA WATER SUPPLY SCHEME, T W NO I, [ MOHAR ] , JJM WORKS, SCHEME CODE SM/18620, APPLICATION NO 2004806860, REFERENCE ID 204348023, SABANG CCC, WBSEDCL |  |  | BILL/01458/2024-2025 | BP-2024-25-421 | 15/07/2024 | 15/07/2024 | WBSEDCL | 5.53 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | SM/18620 | New | Laying distribution pipe line & Accommodate FHTC (300 nos.) under JJM with allied work for Proposed Mohar-Katina (Zone-II) PWSS in Sabang Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000191/2023-2024 | 2805/MD | 07/08/2023 | 02/08/2025 | SANKAR PRASAD MAITY | 73.64 | 0 | 0 | 50
13 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | SM/18620 | New | Laying Rising Main & distribution of Pipe line, Construction of Pump House and Boundary wall and FHTC (786 nos.) work for Proposed Mohar-Katina & its adjoining Mouzas (Zone-I) PWSS, Block- Sabong, Dist: - Paschim Medinipur under Midnapore Division, PHE Dte. [PART-C] | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000286/2023-2024 | 3903/MD | 27/09/2023 | 20/09/2025 | M/S. D.K.H.CONSTRUCTION | 241.34 | 86.19 | 35.71 | 75
14 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | SM/18620 | New | Laying distribution pipe line, Pump House, Boundary wall & Accommodate FHTC (430 nos.) including 2 (Two) years O&M under JJM with allied work for Proposed Mohar-Katina (Zone-II) PWSS in Sabang. Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000400/2023-2024 | 5098/MD | 30/10/2023 | 30/04/2025 | SAI TUBE CO. | 170.59 | 15.91 | 9.33 | 40
15 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | SM/18620 | New | Construction and Commissioning of 2 Nos. O.H.R [400 CuM capacity & 300 CuM Capacity (Both Intze type with pile)] & LDS (Zone-II) for Proposed Mohar-Katina & its adjoining Mouzas (Zone-I & II) PWSS, Block- Sabong, Dist: - Paschim Medinipur under Midnapur Division, PHE Dte. [PART-B] | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000029/2024-2025 | 2118/MD | 09/07/2024 | 01/11/2025 | JAY MATA DI ENTERPRISE | 244.46 | 0 | 0 | 0
16 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | SM/18620 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002724/2023-2024 | 1069/W/MMD | 14/03/2024 | 10/09/2024 | SWAPAN BANERJEE | 10.42 | 0 | 0 | 100
17 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang. | SM/18620 | New | Construction of Approach road at OHR Site of Mohar-Katina (Zone-II) PWSS within Sabang Development block under Midnapore Division P.H.E. Dte. of Paschim Medinipur district. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000372/2024-2025 | 47/MD | 07/01/2025 | 06/02/2025 | SAJAL JANA | 5.35 | 0 | 0 | 100
Total | [13 empty] | 1321.67 | 163.92 | 12.4