## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. | SM/18621 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000389/2023-2024 | 1728/W/MMD | 09/08/2023 | 30/06/2026 | SUBODH KUMAR BANIK | 27.3 | 4.88 | 17.86 | 51
2 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. | SM/18621 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas.under JJM Program under MMD PHE Dte. (Part-II) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000392/2023-2024 | 1731/W/MMD | 09/08/2023 | 05/02/2024 | M/S B.M. ELECTRICAL | 22.89 | 0 | 0 | 50
3 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. | SM/18621 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas.under JJM Program under MMD PHE Dte. (Part-III) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000395/2023-2024 | 1734/W/MMD | 09/08/2023 | 05/02/2024 | KAMAKSHYA ENTERPRISE | 11.98 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. | SM/18621 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 450 & 300 cum OHRs (Intze type with pile foundation) & Accommodate FHTC(5,344 Nos.) under JJM with allied work for Goura (Zone-I,II,III & IV) & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000384/2023-2024 | 5058/MD | 26/10/2023 | 25/06/2026 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 1390.82 | 0 | 0 | 30
5 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. | SM/18621 | New | Material Requisition To Resource Division |  |  | RTOR000041/2022-2023 | 109/MD | 10/01/2023 | 10/01/2023 | Resource Division | 41.59 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. | SM/18621 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 05/01/2025 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. | SM/18621 | New | Material Requisition To Resource Division |  |  | RTOR000028/2024-2025 | 3347/MD | 25/11/2024 | 25/11/2024 | Resource Division | 32.92 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. | SM/18621 | New | Electrict quotation bill for TW-I of Goura (Zone-II) pwss (Ref Consumar ID-204428251),Application No-2004943114,Application Type-New Connection,Name of ccc-Sonakhali ccc, block-Daspur-II |  |  | BILL/03249/2024-2025 | C122406830258 | 05/12/2024 | 05/12/2024 | WBSEDCL | 2.86 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. | SM/18621 | New | Electrict quotation bill for TW-II of Goura (Zone-II) pwss (Ref Consumar ID-204428843),Application No-2004944128,Application Type-New Connection,Name of ccc-Sonakhali ccc, block-Daspur-II |  |  | BILL/03254/2024-2025 | C122406817138 | 05/12/2024 | 05/12/2024 | WBSEDCL | 3.78 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. | SM/18621 | New | Electrict quotation bill for TW-I of Goura (Zone-III) pwss (Ref Consumar ID-204429170),Application No-2004944728,Application Type-New Connection,Name of ccc-Sonakhali ccc, block-Daspur-II |  |  | BILL/03250/2024-2025 | C122406828613 | 05/12/2024 | 05/12/2024 | WBSEDCL | 5.67 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. | SM/18621 | New | Electrict quotation bill for TW-I of Goura (Zone-I) pwss (Ref Consumar ID-204428844),Application No-2004944111,Application Type-New Connection,Name of ccc-Sonakhali ccc, block-Daspur-II |  |  | BILL/03251/2024-2025 | C122406820355 | 06/12/2024 | 06/12/2024 | WBSEDCL | 3.22 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. | SM/18621 | New | Electrict quotation bill for TW-I of Goura (Zone-I) pwss (Ref Consumar ID-204428243),Application No-2004943085,Application Type-New Connection,Name of ccc-Sonakhali ccc, block-Daspur-II |  |  | BILL/03252/2024-2025 | C122406819369 | 05/12/2024 | 05/12/2024 | WBSEDCL | 5.91 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. | SM/18621 | New | Electrict quotation bill for TW-I of Goura (Zone-IV) pwss (Ref Consumar ID-204428246),Application No-2004943045,Application Type-New Connection,Name of ccc-Sonakhali ccc, block-Daspur-II |  |  | BILL/03253/2024-2025 | C122406818522 | 06/12/2024 | 06/12/2024 | WBSEDCL | 3.03 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas. | SM/18621 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002214/2024-2025 | 432/MMSD-I | 26/03/2025 | 23/09/2025 | S.K.ENTERPRISE | 4.11 | 0 | 0 | 0
Total | [13 empty] | 1562.38 | 4.88 | 0.31