## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. | SM/18622 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000383/2023-2024 | 1722/W/MMD | 09/08/2023 | 05/02/2024 | DEY ENTERPRISE | 25.26 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. | SM/18622 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas.under JJM Program under MMD PHE Dte. (Part-II) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000393/2023-2024 | 1732/W/MMD | 09/08/2023 | 05/02/2024 | M/S. JIT ENTERPRISE | 22.78 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. | SM/18622 | New | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 112/MD | 10/01/2023 | 10/01/2023 | Resource Division | 65.54 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. | SM/18622 | New | Laying rising main pipeline for Benai (Zone-I) PWSS under Daspur-II block within Ghatal sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000332/2024-2025 | 3575/MD | 06/12/2024 | 20/01/2025 | M/S. A.R. ENTERPRISE | 5.52 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. | SM/18622 | New | Laying Rising main pipe line for "Benai Zone-II" PWSS under Daspur-II Block within Ghatal Sub-Division under Midnapore Division, P.H.E.Dte | AE Ghatal Sub-division |  | ORD/000127/2024-2025 | 1493/AE/GSD | 24/09/2024 | 24/10/2024 | M/S. A.R. ENTERPRISE | 3.17 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. | SM/18622 | New | Material Requisition To Resource Division |  |  | RTOR000020/2024-2025 | 3340/MD | 25/11/2024 | 25/11/2024 | Resource Division | 25.95 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. | SM/18622 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 cum OHR & 250 Cum OHR (Intze type with pile foundation) & Accommodate FHTC (4,213 Nos.) under JJM with allied work for Benai (Zone- I & Zone-II) & its adjoining mouzas W/S scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000257/2023-2024 | 3231/MD | 11/09/2023 | 31/08/2025 | M/S. A.R. ENTERPRISE. | 983.46 | 317.71 | 32.31 | 15
8 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. | SM/18622 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 05/01/2025 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas. | SM/18622 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002214/2024-2025 | 432/MMSD-I | 26/03/2025 | 23/09/2025 | S.K.ENTERPRISE | 4.11 | 0 | 0 | 0
Total | [13 empty] | 1142.1 | 317.71 | 27.82