## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | BAJGERYA AND ITS ADJOINING MOUZAS PWSS | SM/18658 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAJGERYA AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000386/2023-2024 | 1725/W/MMD | 09/08/2023 | 05/02/2024 | B.P.TRADING CORPORATION | 25.26 | 15.55 | 61.55 | 20
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | BAJGERYA AND ITS ADJOINING MOUZAS PWSS | SM/18658 | New | Sinking of 1 (One) No. Tube well for Bajgerya & its adjoining mouzas PWSS in Keshpur block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. [Part-I] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000200/2023-2024 | 2814/MD | 07/08/2023 | 22/08/2023 | RUPKUMAR KARMAKAR | 8.3 | 7.5 | 90.41 | 100
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | BAJGERYA AND ITS ADJOINING MOUZAS PWSS | SM/18658 | New | Material Requisition To Resource Division |  |  | RTOR000273/2023-2024 | 3986/MD | 06/10/2023 | 06/10/2023 | Resource Division | 33.31 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | BAJGERYA AND ITS ADJOINING MOUZAS PWSS | SM/18658 | New | Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 350 Cum (Intze type with Pile Foundation) & Accommodate FHTC (2904 Nos.) including Two years O&M under JJM with allied work for Bajgerya & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials including 02(Two) Years Operation & Mainatanance within Midnapur Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000015/2024-2025 | 2008/MD | 28/06/2024 | 25/12/2024 | M/S. EL-CON | 971.71 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | BAJGERYA AND ITS ADJOINING MOUZAS PWSS | SM/18658 | New | Sinking of 1 (One) No. Tube well for Bajgerya & its adjoining mouzas PWSS in Keshpur block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. [Part-II] | AE Sadar Sub-division |  | ORD/000056/2024-2025 | 2579/MD | 22/08/2024 | 06/09/2024 | MANNA COMPUTER | 8.3 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | BAJGERYA AND ITS ADJOINING MOUZAS PWSS | SM/18658 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002724/2023-2024 | 1069/W/MMD | 14/03/2024 | 10/09/2024 | SWAPAN BANERJEE | 10.42 | 0 | 0 | 100
7 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | BAJGERYA AND ITS ADJOINING MOUZAS PWSS | SM/18658 | New | ELECTRIC QUOTATION BILL FOR TW NO-I OF BAJGERYA PWSS. REF CONSUMER ID-204325522, APPLICATION NO-2004767121, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/01213/2024-2025 | BP-2024-25-291 | 18/06/2024 | 18/06/2024 | WBSEDCL | 5.83 | 0 | 0 | 0
Total | [13 empty] | 1063.14 | 23.05 | 2.17