## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18696 | New | Material Requisition To Resource Division |  |  | RTOR000175/2023-2024 | 1367/MD | 02/05/2023 | 02/05/2023 | Resource Division | 69.43 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18696 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. (Part-II) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000394/2023-2024 | 1733/W/MMD | 09/08/2023 | 05/02/2024 | ORIENTAL ENGINEERING CO. | 21.57 | 12.46 | 57.76 | 45
3 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18696 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000388/2023-2024 | 1727/W/MMD | 09/08/2023 | 05/02/2024 | HARA PROSAD DAS | 23.73 | 15.56 | 65.55 | 40
4 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18696 | New | Laying Distribution pipeline, Switch Room, Land development & Accommodate FHTC (75 Nos.) under JJM with allied work for Tangasol (Zone-II) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000419/2023-2024 | 5155/MD | 07/11/2023 | 20/01/2025 | RITESH AGARWALL | 25.25 | 0 | 0 | 62
5 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18696 | New | Laying Distribution pipeline & Accommodate FHTC (300 Nos.) under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-VIII] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000421/2023-2024 | 5157/MD | 07/11/2023 | 06/01/2024 | R. CONSTRUCTION | 71.32 | 44.01 | 61.71 | 55
6 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18696 | New | Laying Rising main pipeline & Accommodate FHTC (100 Nos.) under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000402/2023-2024 | 5104/MD | 31/10/2023 | 30/11/2023 | CHANDAN DAS | 15.96 | 3.1 | 19.41 | 68
7 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18696 | New | Laying Distribution pipeline & Accommodate FHTC (300 Nos.) under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-V] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000464/2023-2024 | 5358/MD | 30/11/2023 | 14/01/2024 | S.N.A. CONSTRUCTION | 63.8 | 10.75 | 16.84 | 72
8 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18696 | New | Sinking of 2 (Two) Nos. Tube well for Tangasol & its adjoining mouzas (Zone-II i.e. II/I & II/II) PWSS in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000202/2023-2024 | 2816/MD | 07/08/2023 | 06/09/2023 | MANNA COMPUTER | 11.83 | 10.23 | 86.55 | 100
9 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18696 | New | Sinking of 2 (Two) Nos. Tube well for Tangasol & its adjoining mouzas (Zone-I) PWSS in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000201/2023-2024 | 2815/MD | 07/08/2023 | 06/09/2023 | ANNAPURNA TUBEWELL WORKS | 19.43 | 18.53 | 95.39 | 100
10 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18696 | New | QUOTATION MONEY FOR TUNGASOLE WATER SUPPLY SCHEME, ZONE-I , T W NO II [ NEAR AMGACHIYA ] , KGP-I , JJM WORKS, SCHEME CODE SM/18696, APPLICATION NO 2004580997, REFERENCE ID 204205374, NIMPURA CCC, WBSEDCL |  |  | BILL/04269/2023-2024 | BP-2023-24-790 | 06/03/2024 | 06/03/2024 | WBSEDCL | 5.81 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18696 | New | QUOTATION MONEY FOR TANGASOL WATER SUPPLY SCHEME ( NEAR ICDS ) , JJM WORKS, SCHEME CODE SM/18696, APPLICATION NO 2004580955, REFERENCE ID 204205371, NIMPURA CCC, WBSEDCL |  |  | BILL/03725/2023-2024 | BP-2023-24-698 | 16/02/2024 | 16/02/2024 | WBSEDCL | 4.09 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18696 | New | QUOTATION MONEY FOR TUNGASOLE WATER SUPPLY SCHEME, ZONE-II , T W NO I ,MINI [ NEAR PRIMARY SCHOOL ] , KGP-I , JJM WORKS, SCHEME CODE SM/18696, APPLICATION NO 2004580975, REFERENCE ID 204205372, NIMPURA CCC, WBSEDCL |  |  | BILL/04268/2023-2024 | BP-2023-24-791 | 06/03/2024 | 06/03/2024 | WBSEDCL | 4.12 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18696 | New | QUOTATION MONEY FOR TANGASOL WATER SUPPLY SCHEME ( GALUKSAL ) JJM WORKS, SCHEME CODE SM/18696, APPLICATION NO 2004581010, REFERENCE ID 204205373, NIMPURA CCC, WBSEDCL |  |  | BILL/03726/2023-2024 | BP-2023-24-697 | 16/02/2024 | 16/02/2024 | WBSEDCL | 3.99 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18696 | New | Laying Distribution pipeline & Accommodate FHTC (346 Nos.) under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-VII] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000420/2023-2024 | 5156/MD | 07/11/2023 | 13/01/2026 | GOUTAM PARIA | 53.34 | 0 | 0 | 80
15 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18696 | New | Laying Distribution pipeline & Accommodate FHTC (330 Nos.) under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-VI] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000525/2023-2024 | 5502/MD | 14/12/2023 | 09/04/2025 | SK. SANAMAJ | 85.43 | 0 | 0 | 65
16 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18696 | New | Laying Distribution pipeline & Accommodate FHTC (260 Nos.) including 2 yrs. O&M under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-III] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000524/2023-2024 | 5501/MD | 14/12/2023 | 11/05/2025 | EVEREST CONSULTANT SERVICES | 143.94 | 0 | 0 | 30
17 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18696 | New | Laying Distribution pipeline & Accommodate FHTC (260 Nos.) under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-IV] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000026/2024-2025 | 2079/MD | 04/07/2024 | 03/03/2025 | A R CONSTRUCTION | 84.14 | 17.29 | 20.55 | 68
18 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/18696 | New | Construction of 400 CuM OHR, Pump House & Boundary wall under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | AE Kharagpur Sub-division |  | ORD/000105/2025-2026 | 1237/MD | 28/05/2025 | 24/11/2025 | M/S P.B. ENTERPRISE | 141.67 | 0 | 0 | 0
Total | [13 empty] | 848.83 | 131.92 | 15.54