## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashinathpur & its adjoining mouzas. | SM/18758 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Kashinathpur & its adjoining mouzas under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000744/2023-2024 | 2288/W/MMD | 29/08/2023 | 25/02/2024 | ORIENTAL ENGINEERING CO. | 23.76 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kashinathpur & its adjoining mouzas. | SM/18758 | New | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 75/MD | 09/01/2023 | 09/01/2023 | Resource Division | 22.89 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kashinathpur & its adjoining mouzas. | SM/18758 | New | Material Requisition To Resource Division |  |  | RTOR000029/2024-2025 | 3348/MD | 25/11/2024 | 25/11/2024 | Resource Division | 14.24 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kashinathpur & its adjoining mouzas. | SM/18758 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,311 Nos.) under JJM with allied work for Kashinathpur & its adjoining mouzas W/S Scheme in Daspur- II Block including supply of all labour & materials within Midnapore Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000383/2023-2024 | 5057/MD | 26/10/2023 | 27/03/2026 | DULAL CHANDRA DAS | 602 | 0 | 0 | 25
Total | [13 empty] | 662.88 | 0 | 0