## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | Islampur Piped Water Supply Scheme. | SM/18782 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for ISLAMPUR AND IT'S ADJOINING MOUJAS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001896/2022-2023 | 795/W/MMD | 24/03/2023 | 31/05/2025 | CHAKRABORTY MINING & ENGINEERING | 21.58 | 13.24 | 61.36 | 38
2 | PASCHIM MEDINIPUR | Debra | Midnapore Division | Islampur Piped Water Supply Scheme. | SM/18782 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 450 Cum OHR (Intze type with Pile) & Accommodate FHTC (2,431 Nos.) including Two years O&M under JJM with allied work for Islampur W/S Scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),JE1 Kharagpur Sub-division | ORD/000293/2023-2024 | 3965/MD | 05/10/2023 | 28/03/2025 | M/S. MALLIK CONSTRUCTION | 607.53 | 0 | 0 | 53
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | Islampur Piped Water Supply Scheme. | SM/18782 | New | Material Requisition To Resource Division |  |  | RTOR000270/2023-2024 | 3984/MD | 06/10/2023 | 06/10/2023 | Resource Division | 34.8 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | Islampur Piped Water Supply Scheme. | SM/18782 | New | Electrict quotation bill for TW-I of Islampur pwss (Ref Consumar ID-204444968),Application No-2004963184,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra |  |  | BILL/03039/2024-2025 | C112429789179 | 25/11/2024 | 25/11/2024 | WBSEDCL | 6.34 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | Islampur Piped Water Supply Scheme. | SM/18782 | New | Electrict quotation bill for TW-II of Islampur pwss (Ref Consumar ID-204444970),Application No-2004963217,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra |  |  | BILL/03038/2024-2025 | C112429786723 | 25/11/2024 | 25/11/2024 | WBSEDCL | 6.59 | 0 | 0 | 0
Total | [13 empty] | 676.84 | 13.24 | 1.96