## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Mangrajpur mouzas, Block - Sabang, District - Paschim Medinipur | SM/18785 | New | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Magrajpur, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000018/2022-2023 | 559/W/MMD | 12/04/2022 | 10/08/2022 | M/S NABIN GOPAL SENGUPTA | 6.46 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR | Sabang | Midnapore Mechanical | Ground Based Mini Piped Water Supply Scheme for Mangrajpur mouzas, Block - Sabang, District - Paschim Medinipur | SM/18785 | New | Electric Quotation for MAGRAJPUR (MINIPIPED) Water Supply Scheme, (Ref. ID-203942445) |  |  | BILL/02230/2023-2024 | BP-2023-24-237 | 12/09/2023 | 12/09/2023 | WBSEDCL | 0.1 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Sabang | Midnapore Division | Ground Based Mini Piped Water Supply Scheme for Mangrajpur mouzas, Block - Sabang, District - Paschim Medinipur | SM/18785 | New | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Mangrajpur, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000256/2023-2024 | 3165/MD | 31/08/2023 | 28/02/2025 | SANKAR PRASAD MAITY | 29.51 | 19.83 | 67.18 | 100
Total | [13 empty] | 36.08 | 19.83 | 54.96