## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | Jankapur Piped Water Supply Scheme. | SM/18786 | New | Material Requisition To Resource Division |  |  | RTOR000274/2023-2024 | 3987/MD | 06/10/2023 | 06/10/2023 | Resource Division | 37.09 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | Jankapur Piped Water Supply Scheme. | SM/18786 | New | Material Requisition To Resource Division |  |  | RTOR000128/2024-2025 | 3464/MD | 25/11/2024 | 25/11/2024 | Resource Division | 7.77 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | Jankapur Piped Water Supply Scheme. | SM/18786 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of JANKAPUR PWSS. REF CONSUMER ID-204298988, APPLICATION NO-2004720671, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II |  |  | BILL/00881/2024-2025 | BP-2024-25-180 | 20/05/2024 | 20/05/2024 | WBSEDCL | 2.99 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Mechanical | Jankapur Piped Water Supply Scheme. | SM/18786 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of JANKAPUR PWSS. REF CONSUMER ID-204298990, APPLICATION NO-2004720643, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II |  |  | BILL/00880/2024-2025 | BP-2024-25-181 | 20/05/2024 | 20/05/2024 | WBSEDCL | 3.52 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Dantan-II | Central Drilling | Jankapur Piped Water Supply Scheme. | SM/18786 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
6 | PASCHIM MEDINIPUR | Dantan-II | Midnapore Division | Jankapur Piped Water Supply Scheme. | SM/18786 | New | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 400 (Intze type with Pile) & Accommodate FHTC (2,381 Nos.) including Two years O&M under JJM with allied work for Jankapur & its adjoining mouzas W/S Scheme in Datan-II Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | ORD/000393/2023-2024 | 5067/MD | 26/10/2023 | 13/04/2026 | DIPAK KUMAR BAKLY | 624.05 | 0 | 0 | 10
Total | [13 empty] | 22015.17 | 0 | 0