## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Bural {Zone-I of (I/I & I/II) and II of (II/I & II/II)} & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. | SM/19037 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing Bural PWSS within Sabang Block under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000493/2022-2023 | 2048/MD | 28/09/2022 | 19/10/2022 | GOBINDA MAITY | 10.93 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Bural {Zone-I of (I/I & I/II) and II of (II/I & II/II)} & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. | SM/19037 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at BURAL Water supply scheme, Sabang block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001681/2023-2024 | 59/W/MMD | 15/01/2024 | 13/07/2024 | M/S. SAJAHAN CHOWDHURY | 47.41 | 33.55 | 70.75 | 40
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Bural {Zone-I of (I/I & I/II) and II of (II/I & II/II)} & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. | SM/19037 | Augmentation | Sinking of Tube Well, Laying of Rising Main & Laying of Distribution Pipeline, Construction of 250 Cum RCC OHR, Pump House, Boundary Wall, Repair & Renovation of Existing Structures (i.e.450 Cum & 550 cum RCC OHR, Pump House, Boundary Wall) with allied works to accommodate FHTC (2,382 Nos.) for Augmentation of Bural (ZONE-I & Zone-II) & its Adjoining Mouzas PWSS under Sabang Block under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000827/2023-2024 | 776/MD | 14/03/2024 | 02/06/2026 | NABA KUMAR BHUNIA | 1077.13 | 196.05 | 18.2 | 70
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Bural {Zone-I of (I/I & I/II) and II of (II/I & II/II)} & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. | SM/19037 | Augmentation | QUOTATION MONEY FOR BURAL WATER SUPPLY SCHEME, T W NO 4 / ZONE-I [ KERUR ] , JJM WORKS, SCHEME CODE SM/19037, APPLICATION NO 2004884722, REFERENCE ID 204391136, SABANG CCC, WBSEDCL |  |  | BILL/02444/2024-2025 | BP-2024-25-696 | 27/09/2024 | 27/09/2024 | WBSEDCL | 5.62 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Bural {Zone-I of (I/I & I/II) and II of (II/I & II/II)} & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. | SM/19037 | Augmentation | QUOTATION MONEY FOR BURAL WATER SUPPLY SCHEME, AUGMENTATION , ZONE-II, T W 4, JJM WORKS, SCHEME CODE SM/19037, APPLICATION NO 2004923771, REFERENCE ID 204414194, SABANG CCC, WBSEDCL |  |  | BILL/02978/2024-2025 | BP-2024-25-784 | 12/11/2024 | 12/11/2024 | WBSEDCL | 7.05 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Bural {Zone-I of (I/I & I/II) and II of (II/I & II/II)} & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. | SM/19037 | Augmentation | QUOTATION MONEY FOR BURAL WATER SUPPLY SCHEME, ZONE-I, T W -III, [ GUNDUT ] JJM WORKS, SCHEME CODE SM/19037, APPLICATION NO 2004884758, REFERENCE ID 204391138, SABANG CCC, WBSEDCL |  |  | BILL/02989/2024-2025 | C112422745630 | 18/11/2024 | 18/11/2024 | WBSEDCL | 6.87 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Bural {Zone-I of (I/I & I/II) and II of (II/I & II/II)} & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. | SM/19037 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2025-2026 | 1322/MD | 10/06/2025 | 10/06/2025 | Resource Division | 67.38 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Bural {Zone-I of (I/I & I/II) and II of (II/I & II/II)} & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur. | SM/19037 | Augmentation | THE QUOTATION MONEY FOR BURAL WATER SUPPLY SCHEME, ZONE-I T W NO 05 [ RAMBHADRAPUR ] , JJM WORKS, BLOCK-SABANG, SCHEME CODE SM/19037, APPLICATION NO 2005045949, CONSUMER ID 204497393, SABANG CCC, WBSEDCL |  |  | BILL/04111/2024-2025 | C022539999937 | 18/02/2025 | 18/02/2025 | WBSEDCL | 3.5 | 0 | 0 | 0
Total | [13 empty] | 1225.91 | 229.6 | 18.73