## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Suratpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/19043 | New | Material Requisition To Resource Division |  |  | RTOR000159/2023-2024 | 1282/MD | 28/04/2023 | 28/04/2023 | Resource Division | 190.54 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Suratpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/19043 | New | QUOTATION MONEY FOR SURATPUR WATER SUPPLY SCHEME, T W NO I JJM WORKS, SCHEME CODE SM/19043, APPLICATION NO 2004809647, REFERENCE ID 20352804, DASPUR CCC, WBSEDCL |  |  | BILL/01633/2024-2025 | BP-2024-25-490 | 30/07/2024 | 30/07/2024 | WBSEDCL | 11.24 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Suratpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/19043 | New | QUOTATION MONEY FOR SURATPUR WATER SUPPLY SCHEME, T W NO II, JJM WORKS, SCHEME CODE SM/19043, APPLICATION NO 2004809619, REFERENCE ID 204352803, DASPUR CCC, WBSEDCL. |  |  | BILL/01634/2024-2025 | BP-2024-25-489 | 30/07/2024 | 30/07/2024 | WBSEDCL | 4.78 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Suratpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/19043 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Suratpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001435/2023-2024 | 3089/W/MMD | 29/11/2023 | 07/05/2025 | GOENKA ENTERPRISE | 23.01 | 0 | 0 | 100
5 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Suratpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/19043 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 500 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,144 nos.) under JJM with allied work for Suratpur PWSS in Daspur- I Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance Charge within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000506/2023-2024 | 5514/MD | 15/12/2023 | 27/09/2025 | MASUM ALI KHAN | 694.39 | 259.55 | 37.38 | 30
Total | [13 empty] | 923.97 | 259.55 | 28.09