## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/19044 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Dadpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. [Name of Proposed PWSS Gopalnagar & its adjoining Mouzas PWSS instead of Dadpur & its adjoining Mouzas PWSS] | AE Ghatal Sub-division |  | ORD/000109/2022-2023 | 1065/MD | 02/06/2022 | 22/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5.24 | 5.24 | 100 | 100
2 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/19044 | New | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Gopalnagar & its adjoining Mouzas PWSS instead Dadpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000747/2022-2023 | 1266/MD | 23/06/2022 | 03/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.16 | 2.16 | 100 | 100
3 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/19044 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 500 & 600 cum OHR (Intze type with pile foundation) & Accommodate FHTC (5,406 nos.) under JJM with allied work for Gopalnagar & Kalara PWSS in Daspur-I Block including supply of all labour & materials including Two (02) Years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000229/2023-2024 | 2953/MD | 17/08/2023 | 27/09/2025 | GOBINDA MAITY | 1693.15 | 599.5 | 35.41 | 20
4 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/19044 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001434/2023-2024 | 3088/W/MMD | 29/11/2023 | 07/04/2025 | S.P. ENTERPRISE | 22.95 | 0 | 0 | 80
5 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/19044 | New | Material Requisition To Resource Division |  |  | RTOR000057/2022-2023 | 63/MD | 09/01/2023 | 09/01/2023 | Resource Division | 104.79 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Division | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/19044 | New | Material Requisition To Resource Division |  |  | RTOR000014/2024-2025 | 3335/MD | 25/11/2024 | 25/11/2024 | Resource Division | 15.82 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/19044 | New | QUOTATION MONEY FOR GOPALNAGAR WATER SUPPLY SCHEME, T W - II , JJM WORKS, SCHEME CODE SM/19044, APPLICATION NO 2004702574, REFERENCE ID 204287860, DASPUR CCC, WBSEDCL |  |  | BILL/00829/2024-2025 | BP-2024-25-160 | 13/05/2024 | 13/05/2024 | WBSEDCL | 7.03 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Daspur-I | Midnapore Mechanical | Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. | SM/19044 | New | QUOTATION MONEY FOR GOPALNAGAR WATER SUPPLY SCHEME, T W - I , JJM WORKS, SCHEME CODE SM/19044, APPLICATION NO 2004696196, REFERENCE ID 204284323, DASPUR CCC, WBSEDCL |  |  | BILL/00639/2024-2025 | BP-2024-25-113 | 06/05/2024 | 06/05/2024 | WBSEDCL | 3.55 | 0 | 0 | 0
Total | [13 empty] | 1854.69 | 606.9 | 32.72