## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | SM/19046 | New | Material Requisition To Resource Division |  |  | RTOR000149/2022-2023 | 532/MD | 21/02/2023 | 21/02/2023 | Resource Division | 52.71 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | SM/19046 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. |  |  | ORD/001453/2023-2024 | 3096/W/MMD | 29/11/2023 | 27/05/2024 | SHREE BISHNU CONSTRUCTION | 25.25 | 20.79 | 82.36 | 80
3 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | SM/19046 | New | New Service connection charges. |  |  | BILL/01495/2023-2024 | 88/JMD | 22/03/2024 | 22/03/2024 | WBSEDCL | 7.03 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | SM/19046 | New | Quotation for new service connection at Jhakra T/W-II water supply scheme. |  |  | BILL/00877/2024-2025 | 305/JMD | 14/08/2024 | 14/08/2024 | WBSEDCL | 8.95 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | SM/19046 | New | Laying distribution pipeline, Rising main, Accommodate FHTC (1140 Nos.) including 2yrs. O & M under JJM with allied work for Jhakra PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000633/2023-2024 | 5562/MD | 26/12/2023 | 20/01/2026 | M/S. D.K.H.CONSTRUCTION | 388.07 | 130.64 | 33.66 | 5
6 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | SM/19046 | New | Construction of RCC OHR (400 CuM), Soil investigation, Boundary wall & Accommodate FHTC (1431 Nos.) under JJM with allied work for Jhakra PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000849/2023-2024 | 826/MD | 15/03/2024 | 05/03/2026 | M/S R.N. ENTERPRISE | 233.69 | 0 | 0 | 30
7 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | SM/19046 | New | Laying additional pipeline regarding balance work of distribution network for Jhakra & its adjoining mouza W/S Scheme under Chandrakona-II block within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000478/2024-2025 | 481/MD | 13/02/2025 | 13/07/2025 | NIMAI HAZRA | 37.52 | 0 | 0 | 0
Total | [13 empty] | 753.21 | 151.43 | 20.1