## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | SM/19047 | New | Material Requisition To Resource Division |  |  | RTOR000166/2023-2024 | 1457/MD | 08/05/2023 | 08/05/2023 | Resource Division | 16.87 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | SM/19047 | New | Material Requisition To Resource Division |  |  | RTOR000150/2022-2023 | 533/MD | 21/02/2023 | 21/02/2023 | Resource Division | 57.85 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | SM/19047 | New | Sinking of Tube well, Construction of Pump House & Accommodate FHTC (910 Nos.) under JJM with allied work for Kuapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000460/2023-2024 | 5326/MD | 28/11/2023 | 27/01/2024 | PULLOCK KUMAR GHOSH | 83.89 | 0 | 0 | 30
4 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | SM/19047 | New | Construction of RCC OHR (450 CuM), Soil investigation, Boundary wall & Accommodate FHTC (919 Nos.) under JJM with allied work for Kuapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Ghatal Sub-division |  | ORD/000003/2024-2025 | 1836/MD | 12/06/2024 | 09/12/2024 | S.N ENTERPRISE | 216.01 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Chandrakona-II | Jhargram Mechanical Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | SM/19047 | New | New service connection for Kuapur W/S Scheme. |  |  | BILL/01040/2024-2025 | 380/JMD | 30/09/2024 | 30/09/2024 | WBSEDCL | 3.81 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | SM/19047 | New | Laying distribution pipeline, Rising main, Accommodate FHTC (910 Nos.) including 2yrs. O & M under JJM with allied work for Kuapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000461/2023-2024 | 5327/MD | 28/11/2023 | 26/12/2025 | M/S. D.K.H.CONSTRUCTION | 367.84 | 0 | 0 | 40
7 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Mechanical | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | SM/19047 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. |  |  | ORD/001452/2023-2024 | 3095/W/MMD | 29/11/2023 | 01/06/2025 | JAL PRAVAHIKA PVT. LTD. | 25.24 | 0 | 0 | 90
8 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | SM/19047 | New | Hiring of Inspection vehicle for Jal Jeevan Mission on an ¿as and when required¿ basis, Motor cab (Standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older than 30 (Thirty) months from the date of 1st Registration on daily hire basis for the tenure of 06 (Six months) only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Ghatal Sub-Division, P.H.E Dte. | AE Ghatal Sub-division | JE2 Ghatal Sub-division | ORD/000353/2024-2025 | 1687/AE/GSD | 09/12/2024 | 09/06/2025 | HIRAK KUMAR GHOSH | 0.85 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | SM/19047 | New | Hiring of Inspection vehicle for Jal Jeevan Mission on an ¿as and when required¿ basis, Motor cab (Standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older than 30 (Thirty) months from the date of 1st Registration on daily hire basis for the tenure of 06 (Six months) only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Ghatal Sub-Division, P.H.E Dte. | AE Ghatal Sub-division | JE2 Ghatal Sub-division | ORD/000028/2024-2025 | 1220/AE/GSD | 10/06/2024 | 10/12/2024 | HIRAK KUMAR GHOSH | 0.76 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | SM/19047 | New | Continuation work order for Hiring of Inspection vehicle for Jal Jeevan Mission on an ¿as and when required¿ basis, Motor cab (Standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older than 30 (Thirty) months from the date of 1st Registration on daily hire basis for the tenure of 06 (Six months) only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Ghatal Sub-Division, P.H.E Dte. | AE Ghatal Sub-division |  | ORD/000344/2025-2026 | 962/AE/GSD | 09/12/2025 | 17/05/2026 | HIRAK KUMAR GHOSH | 0.9 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Chandrakona-II | Midnapore Division | THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATEFHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION,PHE DTE. | SM/19047 | New | Continuation order for Hiring of Inspection vehicle for Jal Jeevan Mission on an as and when required basis, Motor cab (Standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older than 30 (Thirty) months from the date of 1st Registration on daily hire basis for the tenure of 06 (Six months) only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Ghatal Sub-Division, P.H.E Dte. | AE Ghatal Sub-division | JE2 Ghatal Sub-division | ORD/000195/2025-2026 | 395/1/AE/GSD | 09/06/2025 | 09/12/2025 | HIRAK KUMAR GHOSH | 0.9 | 0 | 0 | 0
Total | [13 empty] | 774.92 | 0 | 0