## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19048 | New | Material Requisition To Resource Division |  |  | RTOR000094/2022-2023 | 187/MD | 16/01/2023 | 16/01/2023 | Resource Division | 35.98 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19048 | New | Material Requisition To Resource Division |  |  | RTOR000088/2024-2025 | 3440/MD | 25/11/2024 | 25/11/2024 | Resource Division | 18.75 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19048 | New | THE QUOTATION MONEY FOR GOPALI WATER SUPPLY SCHEME, ZONE-II, T W NO I, [ GHOLGHARIA FREE PRIMARY SCHOOL ] , JJM WORKS, SCHEME CODE SM/19048, APPLICATION NO 2004726901, REFERENCE ID 204303571, NIMPURA CCC, WBSEDCL |  |  | BILL/01738/2024-2025 | C072445369106 | 30/07/2024 | 30/07/2024 | WBSEDCL | 2.98 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19048 | New | THE QUOTATION MONEY FOR GOPALI WATER SUPPLY SCHEME, ZONE-II, T W NO I, [ GHOLGHARIA ] , JJM WORKS, SCHEME CODE SM/19048, APPLICATION NO 2004726863, REFERENCE ID 204303571, NIMPURA CCC, WBSEDCL |  |  | BILL/01737/2024-2025 | C072445370570 | 30/07/2024 | 30/07/2024 | WBSEDCL | 3.36 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19048 | New | QUOTATION MONEY FOR GOPALI WATER SUPPLY SCHEME, ZONE- I ,T W NO I [ RANGAMATIA ] , JJM WORKS, SCHEME CODE SM/19048, APPLICATION NO 20047411952, REFERENCE ID 204310973, NIMPURA CCC, WBSEDCL |  |  | BILL/01467/2024-2025 | BP-2024-25-424 | 15/07/2024 | 15/07/2024 | WBSEDCL | 5.89 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19048 | New | QUOTATION MONEY FOR GOPALI WATER SUPPLY SCHEME, ZONE- I, T W NO II, [ GOPALI ] JJM WORKS, SCHEME CODE SM/19048, APPLICATION NO 2004741941, REFERENCE ID 204310971, NIMPURA CCC, WBSEDCL |  |  | BILL/01460/2024-2025 | BP-2024-25-423 | 15/07/2024 | 15/07/2024 | WBSEDCL | 4.31 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19048 | New | Sinking of Tube Wells, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Two nos. 150 cum & 450 cum OHRs & Accommodate FHTC (3,044 Nos.) including Two years O&M under JJM with allied work for Gopali (Zone-I,II) & its adjoining mouzas W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000512/2023-2024 | 5480/MD | 13/12/2023 | 02/12/2025 | SUJOY KUMAR MANDAL | 831.24 | 224.4 | 27 | 66
8 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Gopali (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19048 | New | Construction of boundary wall of Kharagpur Sub-Divisional Store cum Stack yard and Guard Room at Gopali, Mouza ¿ Rangametya, vide J.L. No. - 255, Plot No. - 75/570 under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the district of Paschim Medinipur. | AE Kharagpur Sub-division |  | ORD/000378/2024-2025 | 53/MD | 07/01/2025 | 23/03/2025 | GOBINDA MAITY | 64.56 | 0 | 0 | 0
Total | [13 empty] | 967.07 | 224.4 | 23.2