## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19049 | New | Material Requisition To Resource Division |  |  | RTOR000100/2022-2023 | 181/MD | 16/01/2023 | 16/01/2023 | Resource Division | 48.33 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19049 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II and III) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001441/2023-2024 | 3097/W/MMD | 29/11/2023 | 23/05/2026 | DEBJYOTI BASU | 43.72 | 33.57 | 76.79 | 65
3 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19049 | New | Material Requisition To Resource Division |  |  | RTOR000089/2024-2025 | 3441/MD | 25/11/2024 | 25/11/2024 | Resource Division | 21.6 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19049 | New | QUOTATION MONEY FOR AMBA WATER SUPPLY SCHEME, ZONE-III, T W NO I [ SADATPUR ] , JJM WORKS, SCHEME CODE SM/19049, APPLICATION NO 2004887943, REFERENCE ID 204392629, NIMPURA CCC, WBSEDCL |  |  | BILL/02446/2024-2025 | C092445635685 | 30/09/2024 | 30/09/2024 | WBSEDCL | 6.69 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19049 | New | QUOTATION MONEY FOR AMBA WATER SUPPLY SCHEME, ZONE-I, T W NO 1, [ SUNDRABANDHA ] JJM WORKS, SCHEME CODE SM/19049, APPLICATION NO 2004776663, REFERENCE ID 204331299, NIMPURA CCC, WBSEDCL |  |  | BILL/01463/2024-2025 | BP-2024-25-429 | 16/07/2024 | 16/07/2024 | WBSEDCL | 3.37 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19049 | New | QUOTATION MONEY FOR AMBA WATER SUPPLY SCHEME, ZONE-II, T W NO 2, [ SOBHAPUR ] JJM WORKS, SCHEME CODE SM/19049, APPLICATION NO 2004792617, REFERENCE ID 204341188, NIMPURA CCC, WBSEDCL |  |  | BILL/01462/2024-2025 | BP-2024-25-428 | 16/07/2024 | 16/07/2024 | WBSEDCL | 3.51 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19049 | New | Sinking of Tube wells, Construction of 250 CuM Capacity R.C.C Over Head Reservoirs (Over Raft Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (5415 nos.) including Two years O&M for AMBA (ZONE-I, II & III) & KASHIJORA (ZONE-I & II) Pipe W/S Scheme within Kharagpur-I Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000091/2023-2024 | 2465/MD | 14/07/2023 | 29/09/2025 | GOBINDA MAITY | 1571.51 | 260.73 | 16.59 | 42
8 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19049 | New | Withdrawing the pumping machinaries and installation of Submersible Pump motor set for further extra lowering ( 20 ft ) for each tube well and other works at P H No. 2 of Amba ( Shobhapur ) Water Supply Scheme [ Block Kharagpur-I ] under MMD, PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000610/2025-2026 | 1150/MMSD-I | 14/08/2025 | 21/08/2025 | DEBJYOTI BASU | 0.18 | 0 | 0 | 0
Total | [13 empty] | 1698.91 | 294.3 | 17.32