## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/19050 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 1166/MD | 26/04/2023 | 26/04/2023 | Resource Division | 14.14 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/19050 | Augmentation | Sinking of Tube Well, Construction of 250 Cum OHR including Soil Investigation, Laying distribution pipe line, Pump House, Boundary wall for Augmentation of Barisha (Zone-II) PWSS in Pingla Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000559/2023-2024 | 5513/MD | 15/12/2023 | 12/06/2024 | NIRMAL UDYOG | 366.33 | 0 | 0 | 5
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/19050 | Augmentation | ELECTRIC QUOTATION BILL FOR TW NO-III, Zone -I OF BARISHA PWSS (NARANGADIHI). REF CONSUMER ID-204376280, APPLICATION NO-2004857600, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-PINGLA CCC, NAME OF BLOCK-PINGLA |  |  | BILL/02399/2024-2025 | BP-2024-25-650 | 06/09/2024 | 06/09/2024 | WBSEDCL | 3.6 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/19050 | Augmentation | ELECTRIC QUOTATION BILL FOR ZONE-I , TW NO-III OF BARISHA PWSS. REF CONSUMER ID-204351761, APPLICATION NO-2004812598, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-PINGLA CCC, NAME OF BLOCK-PINGLA |  |  | BILL/01578/2024-2025 | BP-2024-25-459 | 23/07/2024 | 23/07/2024 | WBSEDCL | 3.6 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/19050 | Augmentation | ELECTRIC QUOTATION BILL FOR ZONE-II, TW NO-III OF BARISHA PWSS. REF CONSUMER ID-204391668, APPLICATION NO-2004886574, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-PINGLA CCC, NAME OF BLOCK-PINGLA |  |  | BILL/02428/2024-2025 | C102415730586 | 05/10/2024 | 05/10/2024 | WBSEDCL | 3.31 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/19050 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I and II/II)} and its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001442/2023-2024 | 3098/W/MMD | 29/11/2023 | 22/05/2025 | DEBJYOTI BASU | 34.18 | 0 | 0 | 25
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/19050 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall for Augmentation of Barisha (Zone-I) PWSS in Pingla Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000558/2023-2024 | 5512/MD | 15/12/2023 | 11/09/2025 | KRISHNENDU SEKHAR DAS | 221.3 | 0 | 0 | 35
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I & II/II)} & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/19050 | Augmentation | Laying of Distribution pipe line (extension) for Barisha (Zone-1) PWSS under Pingla Block within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000387/2024-2025 | 59/MD | 07/01/2025 | 17/01/2026 | KRISHNENDU SEKHAR DAS | 48.99 | 0 | 0 | 10
Total | [13 empty] | 695.45 | 0 | 0