## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Dherua & its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/19051 | Augmentation | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001826/2023-2024 | 1685/MMSD-I | 19/12/2023 | 17/02/2024 | M/S BIKASH DE | 0.29 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Dherua & its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/19051 | Augmentation | Fuel for Inspection Vehicle of covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission Program. [w.e.f. 01-01-2024 to 29-02-2024] | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002853/2023-2024 | 1698/MMSD-I | 19/12/2023 | 17/02/2024 | M/S BIKASH DE | 0.83 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Dherua & its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/19051 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing Dherua PWSS within Midnapore Sadar Block under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division |  | ORD/000494/2022-2023 | 2191/MD | 01/11/2022 | 22/11/2022 | UMWELT ENGINEER PVT. LTD. | 16.52 | 15.4 | 93.23 | 100
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Dherua & its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/19051 | Augmentation | Quotation for service connection(Ref ID: 204307608, Application No: 2004733766) for Dherua Augmentation Zone-ii(BHatpara SSK) (SM/19051) under Pirakata CCC,WBSEDCL |  |  | BILL/01224/2024-2025 | BP-2024-25-280 | 14/06/2024 | 14/06/2024 | WBSEDCL | 0.54 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Dherua & its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/19051 | Augmentation | Providing and Installation of pumping machineries and other electromechanical equipments for Augmentation of Dherua and its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001445/2023-2024 | 3101/W/MMD | 29/11/2023 | 22/05/2025 | DEBJYOTI BASU | 90.58 | 16.36 | 18.07 | 30
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Dherua & its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/19051 | Augmentation | Sinking of Tube Well, Construction of RCC OHR (250 Cum & 100 Cum Capacity), Boundary Wall, Pump House and GLR (35 Cum & 75 Cum Capacity) to accommodate FHTC (1,140 Nos) under JJM for Piped Water Supply Scheme under JJM with allied work for Augmentation of Dherua W/S Scheme in Medinipur Sadar Block under Midnapore Sadar Sub Division under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000016/2024-2025 | 2034/MD | 01/07/2024 | 26/06/2025 | M/S. MALLIK CONSTRUCTION | 964.38 | 107.94 | 11.19 | 30
7 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Dherua & its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/19051 | Augmentation | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002834/2023-2024 | 339/MMSD-I | 05/03/2024 | 05/01/2025 | M/S BIKASH DE | 6.3 | 0.14 | 2.17 | 50
8 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Dherua & its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur. | SM/19051 | Augmentation | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Bhatpara SSK , Block - Midnapore Sadar under Midnapore Mechanical Sub Division- I , PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000311/2024-2025 | 1024/MMSD-I | 23/07/2024 | 07/08/2024 | DEBJYOTI BASU | 3.94 | 0 | 0 | 100
Total | [13 empty] | 1083.38 | 139.84 | 12.91