## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, & IV) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19053 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, and IV) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. .(Part-II) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001443/2023-2024 | 3099/W/MMD | 29/11/2023 | 27/05/2024 | SUBHASIS ROY | 11.97 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, & IV) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19053 | New | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 1164/MD | 26/04/2023 | 26/04/2023 | Resource Division | 72.2 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, & IV) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19053 | New | QUOTATION MONEY FOR BHETIA WATER SUPPLY SCHEME, ZONE-I, T W NO II, [ PURBA BHURKUNDI ], KGP-I, JJM WORKS, SCHEME CODE SM/19053, , APPLICATION NO 2004890152, REFERENCE ID 204393530, NIMPURA CCC, WBSEDCL |  |  | BILL/02977/2024-2025 | C112417250894 | 12/11/2024 | 12/11/2024 | WBSEDCL | 3.7 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, & IV) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19053 | New | QUOTATION MONEY FOR BHETIA WATER SUPPLY SCHEME, ZONE-II, T W NO 1, JJM WORKS, SCHEME CODE SM/19053, APPLICATION NO 2004776674, REFERENCE ID 204331298, NIMPURA CCC, WBSEDCL |  |  | BILL/01456/2024-2025 | BP-2024-25-419 | 15/07/2024 | 15/07/2024 | WBSEDCL | 3.1 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, & IV) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19053 | New | QUOTATION MONEY FOR BHETIA WATER SUPPLY SCHEME, ZONE-I, T W NO 1, JJM WORKS, SCHEME CODE SM/19053, APPLICATION NO 2004796950, REFERENCE ID 204343402, NIMPURA CCC, WBSEDCL |  |  | BILL/01457/2024-2025 | BP-2024-25-420 | 15/07/2024 | 15/07/2024 | WBSEDCL | 4.86 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, & IV) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/19053 | New | Sinking of Tube Wells, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 450 cum & 150 cum OHRs & Accommodate FHTC (3,462 Nos.) including Two years O&M under JJM with allied work for Bhetia (Zone-I, II, III & IV) & its adjoining mouzas W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000753/2023-2024 | 216/MD | 31/01/2024 | 27/12/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 1062.32 | 111.73 | 10.52 | 70
Total | [13 empty] | 1158.15 | 111.73 | 9.65