## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Engagement of one no. Sampling Assistant each at (1) Chondrakona Road Sub-District Lab, (2) Chondrakona Town Sub-District Lab, (3) Garbeta Sub-District Lab, (4) Belda Sub-District Lab, (5) Keshiary Sub-District Lab for collecting the water sample from different sources and other allied works and one no. Lab Attendant at (6) Balichak Sub-District Lab under Midnapore Division, P.H.E. Dte. [For the period of 12 (Twelve) months staring from 01.10.2022 to 30.09.2023] | AE/RWS Midnapore Sub Division |  | ORD/000469/2022-2023 | 2061/MD | 30/09/2022 | 30/09/2023 | M/S. EL-CON | 7.76 | 5.06 | 65.19 | 65
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Garhbeta Sub-District Laboratory & (B) Chandrakona Road Sub-District Laboratory within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [For the period of 12 (Twelve) months staring from 01.10.2022 to 30.09.2023] | AE/RWS Midnapore Sub Division |  | ORD/000634/2022-2023 | 2066/MD | 30/09/2022 | 30/09/2023 | UTSAV AGENCY | 7.32 | 7.3 | 99.73 | 60
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Regular analysis, Testing and Monitoring of water samples by experienced & trained personnel for District Water Testing Laboratory activities of Midnapore District Water Testing Laboratory of PHE Dte. at Narampur PHE Complex under Midnapore Sadar Sub-Division, PHE Dte. [Period from 01.01.2022 to 31.12.2022] | AE/RWS Midnapore Sub Division |  | ORD/000535/2021-2022 | 2258/MD | 29/12/2021 | 29/12/2022 | MASUM ALI KHAN | 3.41 | 3.1 | 91.03 | 100
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Chandrakona Municipality Sub-District Laboratory & (B) Ghatal Sub-District Laboratory within Ghatal Sub-Division under Midnapore Division, PHE Dte. [For the period of 12 (Twelve) months staring from 01.10.2022 to 30.09.2023] | AE Ghatal Sub-division |  | ORD/000633/2022-2023 | 2065/MD | 30/09/2022 | 30/09/2023 | UTSAV AGENCY | 7.32 | 7.27 | 99.24 | 100
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Continuation Work Order for Engagement of one no. Sampling Assistant each at (1) Serbera Sub-District Lab, (2) Chondrakona Town Sub-District Lab, (3) Garbeta Sub-District Lab, (4) Belda Sub-District Lab, (5) Keshiary Sub-District Lab for collecting the water sample from different sources and other allied works and one no. Lab Attendant at (6) Balichak Sub-District Lab under Midnapore Division, P.H.E. Dte. [For the period of 04 (Four) months staring from 01.10.2023 to 31.01.2024] | Assistant Engineer (HQ) |  | ORD/000682/2023-2024 | 3888/MD | 27/09/2023 | 27/01/2024 | M/S. EL-CON | 2.47 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Continuation Work Order for Engagement of 3 (Three) Nos. Laboratory Personnel (One Chemist, One Bacteriologist & One Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Kharagpur Sub-District Laboratory within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [For the period of 04 (Four) months staring from 01.10.2023 to 31.01.2024] | AE Kharagpur Sub-division |  | ORD/000683/2023-2024 | 3889/MD | 27/09/2023 | 27/01/2024 | GOBINDA MAITY | 1.19 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Engagement of 3 (Three) Nos. Laboratory Personnel (One Chemist, One Bacteriologist & One Laboratory Assistant) for regular analysis, testing and monitoring of water samples and others allied minor Mtc. works for Kharagpur Sub-District Laboratory within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [For the period of 12 (Twelve) months staring from 01.10.2022 to 30.09.2023] | AE/RWS Midnapore Sub Division |  | ORD/000453/2022-2023 | 2054/MD | 29/09/2022 | 29/09/2023 | GOBINDA MAITY | 3.83 | 3.71 | 96.74 | 10
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Continuation Work Order for Engagement of 2 (Two) Nos. Laboratory Personnel (One Chemist / Bacteriologist & One Laboratory Assistant) of each lab for regular analysis, testing and monitoring of water samples and others allied minor mtc. works for (A) Chandrakona Municipality Sub-District Laboratory & (B) Ghatal Sub-District Laboratory within Ghatal Sub-Division under Midnapore Division, PHE Dte. [For the period of 04 (Four) months staring from 01.10.2023 to 31.01.2024] | AE Ghatal Sub-division |  | ORD/000680/2023-2024 | 3887/MD | 27/09/2023 | 27/01/2024 | UTSAV AGENCY | 2.19 | 2.19 | 100 | 100
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration bill for the NGO Managed Laboratory Personnel from Nov. 2023 to Jan. 2024. |  |  | BILL/01765/2023-2024 | BP-2023-24-739 | 19/03/2024 | 19/03/2024 | ABASH SARADAMOY UNNAYN PARISHAD | 1.35 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration bill of NGO Managed Laboratory for the month of April 2024 to June 2024. |  |  | BILL/00375/2024-2025 | BP-2024-25-250 | 05/08/2024 | 05/08/2024 | SARBIK GRAM BIKASH KENDRA | 1.35 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration of 6 nos NGO - Kangsabati, Keshpur, Belda, Sabang, Abash, Sarbik. |  |  | BILL/00796/2024-2025 | 24-25-423-428 | 04/10/2024 | 04/10/2024 | SIX NOS OF NGO MANAGED LABORATORIES | 0.95 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration bill of NGO Managed Laboratory for the month of April 2024 to June 2024. |  |  | BILL/00372/2024-2025 | BP-2024-25-247 | 05/08/2024 | 05/08/2024 | BELDA SAURYA PRABHA GUCHHA SAMITI | 1.35 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration bill of NGO Managed Laboratory for the month of April 2024 to June 2024. |  |  | BILL/00373/2024-2025 | BP-2024-25-248 | 05/08/2024 | 05/08/2024 | PALLIMANGAL GUCHHA SAMITY | 1.35 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration of the Lab personnel of the NGO managed Laboratory under Midnapore Division, PHE Dte. |  |  | BILL/01053/2023-2024 | BP-2023-24-543 | 17/01/2024 | 17/01/2024 | PALLIMANGAL GUCHHA SAMITY | 1.8 | 0 | 0 | 0
15 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration bill for the NGO Managed Laboratory Personnel from Nov. 2023 to Jan. 2024. |  |  | BILL/01766/2023-2024 | BP-2023-24-740 | 19/03/2024 | 19/03/2024 | SARBIK GRAM BIKASH KENDRA | 1.35 | 0 | 0 | 0
16 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Laboratory Maintenance bill from October 2022 to September 2023. |  |  | BILL/00643/2024-2025 | BP-2024-25-353 | 13/09/2024 | 13/09/2024 | BELDA SAURYA PRABHA GUCHHA SAMITI | 0.75 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration of the Lab personnel of the NGO managed Laboratory under Midnapore Division, PHE Dte. |  |  | BILL/01054/2023-2024 | BP-2023-24-546 | 19/01/2024 | 19/01/2024 | ABASH SARADAMOY UNNAYN PARISHAD | 1.8 | 0 | 0 | 0
18 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration of the Lab personnel of the NGO managed Laboratory under Midnapore Division, PHE Dte. |  |  | BILL/01056/2023-2024 | BP-2023-24-545 | 19/01/2024 | 19/01/2024 | KANGSABATI GUCHHA SAMITY | 1.8 | 0 | 0 | 0
19 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Mobile data recharge of 10 nos. of sub-district laboratories under Midnapore Division, PHE Dte. |  |  | BILL/00137/2024-2025 |  | 21/05/2024 | 21/05/2024 | SUB DISTRICT WATER TESTING LABORATORY | 0.35 | 0 | 0 | 0
20 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Laboratory Maintenance bill from October 2022 to September 2023. |  |  | BILL/00641/2024-2025 | BP-2024-25-352 | 13/09/2024 | 13/09/2024 | KESHPUR SHAHID KSHUDIRAM SEVA SAMITY | 0.75 | 0 | 0 | 0
21 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration of the Lab personnel of the NGO managed Laboratory under Midnapore Division, PHE Dte. |  |  | BILL/01057/2023-2024 | BP-2023-24-547 | 17/01/2024 | 17/01/2024 | SARBIK GRAM BIKASH KENDRA | 1.8 | 0 | 0 | 0
22 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration bill for the NGO Managed Laboratory Personnel from Nov. 2023 to Jan. 2024. |  |  | BILL/01762/2023-2024 | BP-2023-24-736 | 19/03/2024 | 19/03/2024 | KESHPUR SHAHID KSHUDIRAM SEVA SAMITY | 1.35 | 0 | 0 | 0
23 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration of Six Nos. Laboratory Personnel's of NGO Managed Laboratories from February 2024 to March 2024 |  |  | BILL/00102/2024-2025 | BP24-25-100-105 | 28/05/2024 | 28/05/2024 | SIX NOS OF NGO MANAGED LABORATORIES | 5.4 | 0 | 0 | 0
24 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration bill for the NGO Managed Laboratory Personnel from Nov. 2023 to Jan. 2024. |  |  | BILL/01764/2023-2024 | BP-2023-24-738 | 19/03/2024 | 19/03/2024 | PALLIMANGAL GUCHHA SAMITY | 1.35 | 0 | 0 | 0
25 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration bill for the NGO Managed Laboratory Personnel from Nov. 2023 to Jan. 2024. |  |  | BILL/01761/2023-2024 | BP-2023-24-735 | 19/03/2024 | 19/03/2024 | KANGSABATI GUCHHA SAMITY | 1.35 | 0 | 0 | 0
26 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Laboratory Maintenance bill from October 2022 to September 2023. |  |  | BILL/00640/2024-2025 | BP-2023-24-351 | 13/09/2024 | 13/09/2024 | KANGSABATI GUCHHA SAMITY | 0.75 | 0 | 0 | 0
27 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration bill of NGO Managed Laboratory for the month of April 2024 to June 2024. |  |  | BILL/00370/2024-2025 | BP-2024-25-245 | 05/08/2024 | 05/08/2024 | KANGSABATI GUCHHA SAMITY | 1.35 | 0 | 0 | 0
28 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration bill of NGO Managed Laboratory for the month of April 2024 to June 2024. |  |  | BILL/00374/2024-2025 | BP-2024-25-249 | 05/08/2024 | 05/08/2024 | ABASH SARADAMOY UNNAYN PARISHAD | 1.35 | 0 | 0 | 0
29 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration of Laboratory Personnel's i.e Chemist, Bacteriologist and Lab-assistant of 6 nos. NGO managed laboratories under Midnapore Division PHE Dte. for the period from July 2024 to September 2024. |  |  | BILL/00934/2024-2025 | BP-24-25-465-70 | 23/12/2024 | 23/12/2024 | SIX NOS OF NGO MANAGED LABORATORIES | 8.1 | 0 | 0 | 0
30 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration of the Lab personnel of the NGO managed Laboratory under Midnapore Division, PHE Dte. |  |  | BILL/01052/2023-2024 | BP-2023-24-542 | 17/01/2024 | 17/01/2024 | BELDA SAURYA PRABHA GUCHHA SAMITI | 1.8 | 0 | 0 | 0
31 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration bill for the NGO Managed Laboratory Personnel from Nov. 2023 to Jan. 2024. |  |  | BILL/01763/2023-2024 | BP-2023-24-737 | 19/03/2024 | 19/03/2024 | BELDA SAURYA PRABHA GUCHHA SAMITI | 1.35 | 0 | 0 | 0
32 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Laboratory Maintenance bill from October 2022 to September 2023. |  |  | BILL/00644/2024-2025 | BP-2024-25-356 | 13/09/2024 | 13/09/2024 | PALLIMANGAL GUCHHA SAMITY | 0.75 | 0 | 0 | 0
33 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Laboratory Maintenance bill from October 2022 to September 2023. |  |  | BILL/00646/2024-2025 | BP-2024-25-354 | 13/09/2024 | 13/09/2024 | ABASH SARADAMOY UNNAYN PARISHAD | 0.75 | 0 | 0 | 0
34 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration of the Lab personnel of the NGO managed Laboratory under Midnapore Division, PHE Dte. |  |  | BILL/01055/2023-2024 | BP-2023-24-544 | 17/01/2024 | 17/01/2024 | KESHPUR SHAHID KSHUDIRAM SEVA SAMITY | 1.8 | 0 | 0 | 0
35 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Laboratory Maintenance bill from October 2022 to September 2023. |  |  | BILL/00645/2024-2025 | BP-2024-25-355 | 13/09/2024 | 13/09/2024 | SARBIK GRAM BIKASH KENDRA | 0.75 | 0 | 0 | 0
36 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to Water Quality Monitoring & surveillance under Jal Jeevan Mission under Midnapore Division for the FY 2023-2024. | SM/19061 | Support-WQMSP | Remuneration bill of NGO Managed Laboratory for the month of April 2024 to June 2024. |  |  | BILL/00371/2024-2025 | BP-2024-25-246 | 05/08/2024 | 05/08/2024 | KESHPUR SHAHID KSHUDIRAM SEVA SAMITY | 1.35 | 0 | 0 | 0
Total | [13 empty] | 81.81 | 28.63 | 35