## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | GANGANI AND ADJOINING MOUJAS PWSS | SM/19099 | New | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 1194/MD | 26/04/2023 | 26/04/2023 | Resource Division | 115 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | GANGANI AND ADJOINING MOUJAS PWSS | SM/19099 | New | New service connection charges at Gangani TW-II |  |  | BILL/00464/2024-2025 | 222/JMD | 21/06/2024 | 21/06/2024 | WBSEDCL | 3.22 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | GANGANI AND ADJOINING MOUJAS PWSS | SM/19099 | New | New service connection charges at Gangani TW-I |  |  | BILL/00463/2024-2025 | 221/JMD | 21/06/2024 | 21/06/2024 | WBSEDCL | 4.57 | 0 | 0 | 0
Total | [13 empty] | 122.79 | 0 | 0