## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Khukur Daha & its adjoining mouzas. | SM/19101 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Khukur Daha & its adjoining mouzas.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001556/2023-2024 | 3171/W/MMD | 18/12/2023 | 15/06/2024 | NIRMAN | 27.34 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Khukur Daha & its adjoining mouzas. | SM/19101 | New | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 76/MD | 09/01/2023 | 09/01/2023 | Resource Division | 25.83 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Khukur Daha & its adjoining mouzas. | SM/19101 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 450 cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,442) under JJM with allied work for Khukur Daha & its adjoining mouzas W/S Scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000651/2023-2024 | 142/MD | 18/01/2024 | 24/03/2026 | MASUM ALI KHAN | 804.29 | 183.36 | 22.8 | 30
4 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Khukur Daha & its adjoining mouzas. | SM/19101 | New | Material Requisition To Resource Division |  |  | RTOR000030/2024-2025 | 3349/MD | 25/11/2024 | 25/11/2024 | Resource Division | 21.2 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Division | Ground Based Pipe Water Supply Scheme for Khukur Daha & its adjoining mouzas. | SM/19101 | New | Laying rising main & interconnection for Khukurdaha & its adjoining mouzas PWSS within Daspur-II block, Paschim Medinipur district under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000502/2024-2025 | 585/MD | 03/03/2025 | 01/06/2025 | GOBINDA MAITY | 9.16 | 0 | 0 | 95
6 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Khukur Daha & its adjoining mouzas. | SM/19101 | New | Electrict quotation bill for TW-I of Khukurdaha pwss (Ref Consumar ID-204483093),Application No-2005024680,Application Type-New Connection,Name of CCC-Sonakhali ccc, block-Daspur-II |  |  | BILL/04204/2024-2025 | C032554797599 | 17/03/2025 | 17/03/2025 | WBSEDCL | 2.81 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Daspur-II | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Khukur Daha & its adjoining mouzas. | SM/19101 | New | Electrict quotation bill for TW-II of Khukurdha pwss (Ref Consumar ID-204668396),Application No-2005320427,Application Type-New Connection,Name of CCC-Sonakhali ccc, block-Daspur-II. |  |  | BILL/02620/2025-2026 |  | 10/09/2025 | 10/09/2025 | WBSEDCL | 7.25 | 0 | 0 | 0
Total | [13 empty] | 897.89 | 183.36 | 20.42