## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I | SM/19102 | New | Material Requisition To Resource Division |  |  | RTOR000052/2022-2023 | 66/MD | 09/01/2023 | 09/01/2023 | Resource Division | 54.01 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I | SM/19102 | New | Material Requisition To Resource Division |  |  | RTOR000090/2024-2025 | 3442/MD | 25/11/2024 | 25/11/2024 | Resource Division | 25.77 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I | SM/19102 | New | QUOTATION MONEY FOR GOKULPUR MINI WATER SUPPLY SCHEME,ZONE-III, T W NO I [ LELUAKOLA ] ,JJM WORKS, SCHEME CODE SM/19102, APPLICATION NO 2004793778, REFERENCE ID 204340985, NIMPURA CCC, WBSEDCL |  |  | BILL/01466/2024-2025 | BP-2024-25-430 | 16/07/2024 | 16/07/2024 | WBSEDCL | 0.11 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I | SM/19102 | New | QUOTATION MONEY FOR GOKULPUR WATER SUPPLY SCHEME, ZONE-II, T W NO I [ KESHPAL] , JJM WORKS, SCHEME CODE SM/19102, APPLICATION NO 2004825721, REFERENCE ID 204360221, NIMPURA CCC, WBSEDCL |  |  | BILL/01855/2024-2025 | C082408994649 | 07/08/2024 | 07/08/2024 | WBSEDCL | 4.01 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I | SM/19102 | New | QUOTATION MONEY FOR GOKULPUR WATER SUPPLY SCHEME, ZONE-III, T W NO II [ WALIPUR] , JJM WORKS, SCHEME CODE SM/19102, BLOCK- KHARAGPUR-I, APPLICATION NO 2004831803, REFERENCE ID 204363828, NIMPURA CCC, WBSEDCL |  |  | BILL/01854/2024-2025 | C082408995334 | 07/08/2024 | 07/08/2024 | WBSEDCL | 3.81 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I | SM/19102 | New | Sinking of Tube Well, Laying distribution pipe line, Rising main, Pump House, Boundary wall, Soil investigation, Construction of 450 (Intze type with pile foundation) & 250 & 400 cum OHRs (Intze type with solid raft) & Accommodate FHTC (6,370 Nos.) including Two years O&M under JJM with allied work for (1) Gokulpur (Zone-I,II & III ) and (2) Risa & its adjoining mouzas W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000094/2023-2024 | 2466/MD | 14/07/2023 | 18/04/2026 | GOBINDA MAITY | 1715.83 | 0 | 0 | 30
7 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I | SM/19102 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, and III) and its adjoining mouzas, Block - Kharagpur-Iunder JJM Program under MMD PHE Dte. (Zone-III) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001558/2023-2024 | 3173/W/MMD | 18/12/2023 | 02/04/2026 | RISHAV ENTERPRISE | 5.98 | 0 | 0 | 85
8 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I | SM/19102 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-Iunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001667/2023-2024 | 54/W/MMD | 15/01/2024 | 01/04/2026 | M/S BARMAN ROY TRADERS | 25.52 | 0 | 0 | 75
9 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I | SM/19102 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, and III) and its adjoining mouzas, Block - Kharagpur-Iunder JJM Program under MMD PHE Dte.(Zone-II) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001557/2023-2024 | 3172/W/MMD | 18/12/2023 | 10/06/2025 | S.S.GHORAI | 22.89 | 0 | 0 | 100
Total | [13 empty] | 1857.93 | 0 | 0