## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to WQMSP under Jal Jeevan Mission for 12 months( April 24 to March 25) | SM/19285 | Support-WQMSP | Engagement of Laboratory Personnel (One Chemist, One Bacteriologist, One Laboratory Assistant & One Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor mtc. works of 11 Nos. Water Testing Laboratory under Midnapore Division, PHE Dte. [For the period of 12 (Twelve) months i.e. from 01.02.2025 to 31.01.2026] | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000450/2024-2025 | 371/MD | 31/01/2025 | 31/01/2026 | CFS MANAGEMENT PVT. LTD. | 92.03 | 0 | 0 | 75
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to WQMSP under Jal Jeevan Mission for 12 months( April 24 to March 25) | SM/19285 | Support-WQMSP | Regular analysis, Testing and Monitoring of water samples by experienced & trained personnel for District Water Testing Laboratory activities of Midnapore District Water Testing Laboratory of PHE Dte. at Narampur PHE Complex under Midnapore Sadar Sub-Division, PHE Dte. [For the period of 03 (Three) months starting from 15.06.2024 to 14.09.2024] | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000068/2024-2025 | 1863/MD | 14/06/2024 | 14/09/2024 | GOBINDA MAITY | 1.63 | 0 | 0 | 100
Total | [13 empty] | 93.66 | 0 | 0