## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to WQMSP under Jal Jeevan Mission for 12 months( April 24 to March 25) | SM/19285 | Support-WQMSP | Regular analysis, Testing and Monitoring of water samples by experienced & trained personnel for District Water Testing Laboratory activities of Midnapore District Water Testing Laboratory of PHE Dte. at Narampur PHE Complex under Midnapore Sadar Sub-Division, PHE Dte. [For the period of 03 (Three) months starting from 15.06.2024 to 14.09.2024] | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000068/2024-2025 | 1863/MD | 14/06/2024 | 14/09/2024 | GOBINDA MAITY | 1.63 | 1.33 | 81.26 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to WQMSP under Jal Jeevan Mission for 12 months( April 24 to March 25) | SM/19285 | Support-WQMSP | Continuation Work Order for "Regular analysis, Testing and Monitoring of water samples by experienced & trained personnel for District Water Testing Laboratory activities of Midnapore District Water Testing Laboratory of PHE Dte. at Narampur PHE Complex under Midnapore Sadar Sub-Division, PHE Dte. [For the period of 2.5 (Two point Five) months starting from 15.09.2024 to 30.11.2024]" | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000359/2024-2025 | 2901/MD | 13/09/2024 | 29/11/2024 | GOBINDA MAITY | 1.23 | 0.99 | 80.83 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to WQMSP under Jal Jeevan Mission for 12 months( April 24 to March 25) | SM/19285 | Support-WQMSP | Engagement of 2 (Two) Nos Laboratory Personnel ( One Chemist / Bacteriologist & One Laboratory Assistant )Regular analysis, Testing and Monitoring of water samples by experienced & trained personnel for Water Testing Laboratory activities of 05 nos Sub-District Water Testing Laboratory of PHE Dte. at Balichak SDL, Bhikni Nischintapur SDL, Dantan SDL, Belda SDL, Keshiary SDL(For 01(One) month]., Similarly Bhikni Nischintapur SDL, (For 02(Two) months]. under Midnapur Division , P.H.E Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra) | ORD/000558/2024-2025 | 72/RWS/MID | 22/01/2025 | 23/03/2025 | UTSAV AGENCY | 1.93 | 1.93 | 100 | 100
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to WQMSP under Jal Jeevan Mission for 12 months( April 24 to March 25) | SM/19285 | Support-WQMSP | Continuation Work Order for "Regular analysis, Testing and Monitoring of water samples by experienced & trained personnel for District Water Testing Laboratory activities of Midnapore District Water Testing Laboratory of PHE Dte. at Narampur PHE Complex under Midnapore Sadar Sub-Division, PHE Dte. [For the period of 02 (Two) months starting from 01.12.2024 to 31.01.2025]" | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000521/2024-2025 | 3510/MD | 29/11/2024 | 29/01/2025 | GOBINDA MAITY | 0.99 | 0.79 | 80.6 | 100
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to WQMSP under Jal Jeevan Mission for 12 months( April 24 to March 25) | SM/19285 | Support-WQMSP | Submission of Laboratory Maintenance Bill from October 2023 to September 2024 of Six nos. NGO managed laboratories. |  |  | BILL/01002/2025-2026 |  | 07/12/2025 | 07/12/2025 | SIX NOS OF NGO MANAGED LABORATORIES | 4.5 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to WQMSP under Jal Jeevan Mission for 12 months( April 24 to March 25) | SM/19285 | Support-WQMSP | Remuneration to the Laboratory Personnel. for the period from October 2024 to December 2024. |  |  | BILL/00139/2025-2026 | 42152 | 17/07/2025 | 17/07/2025 | SIX NOS OF NGO MANAGED LABORATORIES | 8.1 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to WQMSP under Jal Jeevan Mission for 12 months( April 24 to March 25) | SM/19285 | Support-WQMSP | Submission of Remuneration Bill from September 2025 to October 2025 of Six nos NGO managed laboratories. |  |  | BILL/01003/2025-2026 |  | 07/12/2025 | 07/12/2025 | SIX NOS OF NGO MANAGED LABORATORIES | 5.4 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to WQMSP under Jal Jeevan Mission for 12 months( April 24 to March 25) | SM/19285 | Support-WQMSP | Remuneration to the Laboratory personnel's t.e chemist, bacteriologist and and Lab-assistant of 6 nos NGO managed laboratories under Midnapore Division, PHE Dte. |  |  | BILL/01415/2024-2025 | BP-24-25-564-69 | 28/03/2025 | 28/03/2025 | SIX NOS OF NGO MANAGED LABORATORIES | 8.1 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to WQMSP under Jal Jeevan Mission for 12 months( April 24 to March 25) | SM/19285 | Support-WQMSP | Engagement of Laboratory Personnel (One Chemist, One Bacteriologist, One Laboratory Assistant & One Sampling Assistant) for regular analysis, testing and monitoring of water samples and others allied minor mtc. works of 11 Nos. Water Testing Laboratory under Midnapore Division, PHE Dte. [For the period of 12 (Twelve) months i.e. from 01.02.2025 to 31.01.2026] | AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division | ORD/000450/2024-2025 | 371/MD | 31/01/2025 | 31/01/2026 | CFS MANAGEMENT PVT. LTD. | 92.03 | 46.01 | 50 | 75
10 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to WQMSP under Jal Jeevan Mission for 12 months( April 24 to March 25) | SM/19285 | Support-WQMSP | Remuneration to the Laboratory Personnel's i.e chemist, Bacteriologist and Lab-assistant of 6 NGO managed laboratories under Midnapore Division, PHE Dte. for the period of November 2025 to January 2025 of Six Nos NGO. |  |  | BILL/01437/2025-2026 |  | 26/02/2026 | 26/02/2026 | SIX NOS OF NGO MANAGED LABORATORIES | 8.1 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Division | Operational charges of PHED & NGO managed laboratories related to WQMSP under Jal Jeevan Mission for 12 months( April 24 to March 25) | SM/19285 | Support-WQMSP | Remuneration and Festival Bonus bill for the FY 2023-24 of 6nos NGO Manage Laboratory Personnel. for the period from July 2025 to August 2025. |  |  | BILL/00959/2025-2026 |  | 21/11/2025 | 21/11/2025 | SIX NOS OF NGO MANAGED LABORATORIES | 6.48 | 0 | 0 | 0
Total | [13 empty] | 138.48 | 51.06 | 36.87