## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000095/2023-2024 | 1307/W/MMD | 15/05/2023 | 13/08/2023 | A.K. INDUSTRIES | 231.59 | 177.59 | 76.68 | 83
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp AT BASANTAPUR WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 202781424, APPLICATION NO 2004704970, DASPUR CCC [ SCHEME CODE SM/16928 ] |  |  | BILL/00826/2024-2025 | BP-2024-25-445 | 16/07/2024 | 16/07/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp AT KHANJAPUR WATER SUPPLY SCHEME , P H NO II, CONSUMER ID 201201978, APPLICATION NO 2004704971, DASPUR CCC [ SCHEME CODE SM/16928 ] |  |  | BILL/00827/2024-2025 | BP-2024-25-444 | 16/07/2024 | 16/07/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | CHARGES OF GENERATION METER [ NET METERING ] FOR SOLAR POWER PLANT OF 10 KWp AT BHEMWA WATER SUPPLY SCHEME , ZONE-II, P H NO 1, CONSUMER ID 200781300, APPLICATION NO 2004697971, SABANG CCC |  |  | BILL/01724/2024-2025 |  | 24/07/2024 | 24/07/2024 | WBSEDCL | 0.18 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp AT SUPAPURSURI WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 201453480, APPLICATION NO 2004704898, DASPUR CCC [ SCHEME CODE SM/16928 ] |  |  | BILL/00831/2024-2025 | BP-2024-25-442 | 16/07/2024 | 16/07/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | APPLICATION FFE FOR SOLAR POWER PLANT OF 10 KWp AT BHEMWA WATER SUPPLY SCHEME , ZONE-II, P H NO 1, CONSUMER ID 200781300, APPLICATION NO 2004697971, SABANG CCC |  |  | BILL/01301/2024-2025 | BP-2024-25-439 | 16/07/2024 | 16/07/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp AT NARAYANBAR WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 200452363, APPLICATION NO 2004769900, SABANG CCC |  |  | BILL/01300/2024-2025 | BP-2024-25-438 | 16/07/2024 | 16/07/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | CHARGES OF GENERATION METER [ NET METERING ] FOR SOLAR POWER PLANT OF 10 KWp AT BHEMWA WATER SUPPLY SCHEME , ZONE-I, P H NO 1, CONSUMER ID 200781302, APPLICATION NO 2004697991, SABANG CCC |  |  | BILL/01729/2024-2025 | BP-2024-25-514 | 31/07/2024 | 31/07/2024 | WBSEDCL | 0.18 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp FOR BURAL WATER SUPPLY SCHEME, ZONE- II , T W NO I , JJM WORKS, SCHEME CODE SM/16928, APPLICATION NO 2004697989 , CONSUMER ID 200452395, SABANG CCC, WBSEDCL |  |  | BILL/01216/2024-2025 | BP-2024-25-433 | 16/07/2024 | 16/07/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | CHARGES OF GENERATION METER [ NET METERING ] FOR SOLAR POWER PLANT OF 10 KWp AT SHYASUNDARPUR WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 201045814, APPLICATION NO 2004697999, SABANG CCC |  |  | BILL/01725/2024-2025 |  | 24/07/2024 | 24/07/2024 | WBSEDCL | 0.18 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | APPLICATION FFE FOR SOLAR POWER PLANT OF 10 KWp AT BISHNUPUR WATER SUPPLY SCHEME , P H NO 1, BLOCK SABANG, CONSUMER ID 200461276, APPLICATION NO 2004769914, SABANG CCC |  |  | BILL/01302/2024-2025 | BP-2024-25-437 | 16/07/2024 | 16/07/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | CHARGES OF GENERATION METER [ NET METERING ] FOR SOLAR POWER PLANT OF 10 KWp AT SABANG WATER SUPPLY SCHEME , ZONE-I, P H NO 1, CONSUMER ID 212013535, APPLICATION NO 2004697968, SABANG CCC |  |  | BILL/01727/2024-2025 | BP-2024-25-570 | 14/08/2024 | 14/08/2024 | WBSEDCL | 0.18 | 0 | 0 | 0
13 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp FOR SHYAMSUNDARPUR WATER SUPPLY SCHEME, T W NO I , JJM WORKS, SCHEME CODE SM/16928, APPLICATION NO 2004697999 , CONSUMER ID 201045814, SABANG CCC, WBSEDCL |  |  | BILL/01220/2024-2025 | BP-2024-25-436 | 16/07/2024 | 16/07/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
14 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp FOR BURAL WATER SUPPLY SCHEME, ZONE- I , T W NO I , JJM WORKS, SCHEME CODE SM/16928, APPLICATION NO 2004697958 , CONSUMER ID 200292721, SABANG CCC, WBSEDCL |  |  | BILL/01215/2024-2025 | BP-2024-25-432 | 16/07/2024 | 16/07/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
15 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | QUOTATION MONEY FOR NET METERING FOR 10 KWp SOLAR POWER PLANT AT TARARUI WATER SUPPLY SCHEME , TW NO 1, SCHEME CODE SM/16928 , BLOCK DANTAN, DANTAN CCC [ APPLICATION NO 2004684098, CONSUMER ID 202834255 ] |  |  | BILL/00651/2024-2025 | BP-2024-24-124 | 06/05/2024 | 06/05/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
16 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp AT KANJAPUR WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 201201977, APPLICATION NO 2004704974, DASPUR CCC [ SCHEME CODE SM/16928 ] |  |  | BILL/00830/2024-2025 | BP-2024-25-443 | 16/07/2024 | 16/07/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
17 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | APPLICATION FFE FOR SOLAR POWER PLANT OF 10 KWp AT KATAN WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 201975256, APPLICATION NO 2004704975, DASPUR CCC [ SCHEME CODE SM/16928 ] |  |  | BILL/00833/2024-2025 | BP-2024-25-440 | 16/07/2024 | 16/07/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
18 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp FOR SABANG WATER SUPPLY SCHEME, ZONE-I, T W NO I JJM WORKS, SCHEME CODE SM/16928, APPLICATION NO 2004697968 , CONSUMER ID 212013535, SABANG CCC, WBSEDCL |  |  | BILL/01219/2024-2025 | BP-2024-25-435 | 16/07/2024 | 16/07/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
19 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | CHARGES OF GENERATION METER [ NET METERING ] FOR SOLAR POWER PLANT OF 10 KWp AT KAPASDA WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 200292702, APPLICATION NO 2004697950, SABANG CCC |  |  | BILL/01723/2024-2025 | BP-2024-25-513 | 31/07/2024 | 31/07/2024 | WBSEDCL | 0.2 | 0 | 0 | 0
20 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | CHARGES OF GENERATION METER [ NET METERING ] FOR SOLAR POWER PLANT OF 10 KWp AT BURAL WATER SUPPLY SCHEME , ZONE - I, P H NO 1, CONSUMER ID 200292721, APPLICATION NO 2004697958, SABANG CCC |  |  | BILL/01726/2024-2025 |  | 24/07/2024 | 24/07/2024 | WBSEDCL | 0.18 | 0 | 0 | 0
21 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | APPLICATION FFE FOR SOLAR POWER PLANT OF 10 KWp AT BACHRAKUNDU WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 201514664, APPLICATION NO 2004704979, DASPUR CCC [ SCHEME CODE SM/16928 ] |  |  | BILL/00832/2024-2025 | BP-2024-25-441 | 16/07/2024 | 16/07/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
22 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | Quotation for Application Fee of Solar Power Plant 10 KW at PH-I of PURULDA PWSS . Application No-2004602453, Ref Consumer ID-202975691, Billing Type-Net Billing, Name of CCC-Khakurda CCC. |  |  | BILL/03945/2023-2024 | BP-2023-24-732 | 26/02/2024 | 26/02/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
23 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | APPLICATION FFE FOR SOLAR POWER PLANT OF 10 KWp AT BHEMWA WATER SUPPLY SCHEME ,ZONE- I , P H NO 1, SCHEME CODE SM/16928, CONSUMER ID 200781302, APPLICATION NO 2004697991, SABANG CCC |  |  | BILL/01217/2024-2025 | BP-2024-25-434 | 16/07/2024 | 16/07/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
24 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | CHARGES OF GENERATION METER [ NET METERING ] FOR SOLAR POWER PLANT OF 10 KWp AT BURAL WATER SUPPLY SCHEME , ZONE-II, P H NO 1, CONSUMER ID 2004523395, APPLICATION NO 2004697989, SABANG CCC |  |  | BILL/01728/2024-2025 | BP-2024-25-515 | 31/07/2024 | 31/07/2024 | WBSEDCL | 0.18 | 0 | 0 | 0
25 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | APPLICATION FEE FOR SOLAR POWER PLANT OF 10 KWp FOR KAPASDA WATER SUPPLY SCHEME, T W NO I , JJM WORKS, SCHEME CODE SM/16928, APPLICATION NO 2004697950 , CONSUMER ID 200292702, SABANG CCC, WBSEDCL |  |  | BILL/01214/2024-2025 | BP-2024-25-431 | 16/07/2024 | 16/07/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
26 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going IOT based scheme as per Annexure-C under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000018/2024-2025 | 720/MMSD-I | 07/06/2024 | 22/06/2024 | SUBHASIS ROY | 2.29 | 0.25 | 11.15 | 100
27 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going IOT based scheme as per Annexure-B under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000017/2024-2025 | 719/MMSD-I | 07/06/2024 | 22/06/2024 | SUBHASIS ROY | 2.29 | 2.29 | 100 | 100
28 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | Providing and installation of scheme information board on Solarisation and Rejuvenation JJM works at different PWSS in Pingla, Keshiary, Dantan-I, Dantan-II, Garbeta-II and Keshpur Block, Dist.- Paschim Medinipur under JJM Program under Midnapore Mechanical Division, P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000010/2024-2025 | 712/MMSD-I | 07/06/2024 | 22/06/2024 | MUKHERJEE ART CENTRE | 5.1 | 0.22 | 4.34 | 100
29 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going IOT based scheme as per Annexure-D under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000032/2024-2025 | 721/MMSD-I | 07/06/2024 | 22/06/2024 | SUBHASIS ROY | 2.29 | 0.38 | 16.62 | 100
30 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | Supply and installation of sign board for depicting the scheme details of different on-going IOT based scheme as per Annexure-A under JJM works for the purpose of Geotagging under Midnapore Mechanical Division, P.H.E. Dte. Dist. - Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000016/2024-2025 | 718/MMSD-I | 07/06/2024 | 22/06/2024 | SUBHASIS ROY | 2.29 | 2.29 | 100 | 100
31 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | CHARGES OF GENERATION METER [ NET METERING ] FOR SOLAR POWER PLANT OF 10 KWp AT KATAN WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 201975256, APPLICATION NO 2004704975, DASPUR CCC. |  |  | BILL/03970/2024-2025 | C022508297298 | 04/02/2025 | 04/02/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
32 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | QUOTATION FOR GENERATION METER [ NET-METERING ] REGARDING SOLARISATION AT T W NO 01 OF NARAYANBAR WATER SUPPLY SCHEME , SCHEME CODE SM/16928, BLOCK-SABANG, SABANG CCC |  |  | BILL/00394/2025-2026 | W/267/25-26 | 07/08/2025 | 07/08/2025 | WBSEDCL | 0.31 | 0 | 0 | 0
33 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | CHARGES OF GENERATION METER [ NET METERING ] FOR SOLAR POWER PLANT OF 10 KWp AT BACHRAKUNDU WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 201514664, APPLICATION NO 2004704979, DASPUR CCC. |  |  | BILL/03971/2024-2025 | C022508318596 | 04/02/2025 | 04/02/2025 | WBSEDCL | 0.23 | 0 | 0 | 0
34 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | PROVIDING SOLARIZATION OF WBSEDCL ENERGISED PUMPING INSTALLATIONS AT PURULDA AND ITS ADJACENT WATER SUPPLY SCHEME UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION PHE | SM/16928 | Solarisation | CHARGES OF GENERATION METER [ NET METERING ] FOR SOLAR POWER PLANT OF 10 KWp AT BASANTAPUR WATER SUPPLY SCHEME , P H NO 1, CONSUMER ID 202781424, APPLICATION NO 2004704970, DASPUR CCC. |  |  | BILL/03973/2024-2025 | C022508361750 | 04/02/2025 | 04/02/2025 | WBSEDCL | 0.22 | 0 | 0 | 0
Total | [13 empty] | 248.22 | 183.02 | 73.73