## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation Sauri Kotbar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17300 | Solarisation | Solarization of grid connected pumping installation Sauri Kotbar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001762/2022-2023 | 676/W/MMD | 23/03/2023 | 19/09/2023 | M/S B.M. ELECTRICAL | 6.26 | 4.89 | 78.03 | 70
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation Sauri Kotbar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17300 | Solarisation | Providing and installation of scheme information board on Smart water supply measurement and monitoring system JJM works at different PWSS in Pingla, Keshiary, Dantan-I, Dantan-II, Garbeta-II and Keshpur Block, Dist.- Paschim Medinipur under JJM Program under Midnapore Mechanical Division, P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000011/2024-2025 | 713/MMSD-I | 07/06/2024 | 22/06/2024 | SUBHASIS ROY | 4.04 | 0.18 | 4.54 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation Sauri Kotbar PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17300 | Solarisation | Providing and installation of scheme information board on Solarisation and Rejuvenation JJM works at different PWSS in Pingla, Keshiary, Dantan-I, Dantan-II, Garbeta-II and Keshpur Block, Dist.- Paschim Medinipur under JJM Program under Midnapore Mechanical Division, P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000010/2024-2025 | 712/MMSD-I | 07/06/2024 | 22/06/2024 | MUKHERJEE ART CENTRE | 5.1 | 0.23 | 4.41 | 100
Total | [13 empty] | 15.4 | 5.29 | 34.37