## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Dantan PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | SM/17321 | Solarisation | Solarization of grid connected pumping installation at Dantan PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001768/2022-2023 | 685/W/MMD | 23/03/2023 | 19/09/2023 | SUBHRA ENTERPRISE | 6.26 | 4.89 | 78.03 | 80
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Dantan PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | SM/17321 | Solarisation | Quotation for Application fee of Solar Power Plant 10 KW at PH-II of Dantan PWSS. Application No-2004558445. Ref Consumer ID-212061369.Billing Type-NET BILLING. Name of CCC-Dantan CCC. SCHEME CODE-SM/17321 |  |  | BILL/03561/2023-2024 | BP-2023-24-631 | 08/02/2024 | 08/02/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Dantan PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | SM/17321 | Solarisation | Providing and installation of scheme information board on Solarisation and Rejuvenation JJM works at different PWSS in Pingla, Keshiary, Dantan-I, Dantan-II, Garbeta-II and Keshpur Block, Dist.- Paschim Medinipur under JJM Program under Midnapore Mechanical Division, P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000010/2024-2025 | 712/MMSD-I | 07/06/2024 | 22/06/2024 | MUKHERJEE ART CENTRE | 5.1 | 0.44 | 8.69 | 100
Total | [13 empty] | 11.36 | 5.33 | 46.88