## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Khasbar, Zone-I & Zone-II PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | SM/17326 | Solarisation | Solarization of grid connected pumping installation at Khasbar, Zone-I & Zone-II PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001835/2022-2023 | 694/W/MMD | 23/03/2023 | 19/09/2023 | A.K. INDUSTRIES | 12.52 | 10.02 | 80 | 80
Total | [13 empty] | 12.52 | 10.02 | 80