## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Keshiary PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | SM/17342 | Solarisation | Solarization of grid connected pumping installation at Keshiary PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001831/2022-2023 | 691/W/MMD | 23/03/2023 | 19/09/2023 | SWITCHING AVO ELECTRO POWER LTD | 6.26 | 4.86 | 77.57 | 70
Total | [13 empty] | 6.26 | 4.86 | 77.57