## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation at Jatra Bansiriasole PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | SM/17377 | Solarisation | Solarization of grid connected pumping installation at Jatra Bansiriasole PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001882/2022-2023 | 780/W/MMD | 24/03/2023 | 20/09/2023 | MANORANJAN DEY | 6.26 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Jhargram Mechanical Division | Solarization of grid connected pumping installation at Jatra Bansiriasole PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | SM/17377 | Solarisation | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | Driller-In-Charge | Junior Engineer | ORD/000725/2024-2025 | 6881/JMD | 05/09/2024 | 05/10/2024 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
Total | [13 empty] | 9.27 | 0 | 0