## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Design, development, supply and installation of smart water supply measurement & Monitoring system at Jote Ghanashyam PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte | SM/17476 | IOT | Implementation of IOT based monitoring of rural water supply in the district of Paschim Medinipur and Purba Medinipur under Midnpore Mechanical Division P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Junior Engineer, Haldia Electrical Sub-Division,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division.,Sri Antu Kr Roy, JE/Midnapur Mechanical Sub-Division-I,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Sourav Mondal, JE/Midnapur Mechanical Sub-Division-,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000551/2025-2026 | 2068/W/MMD | 03/12/2025 | 05/10/2026 | WEBEL TECHNOLOGY LIMITED | 3942.93 | 0 | 0 | 30
Total | [13 empty] | 3942.93 | 0 | 0