## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation Kasanda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17733 | Solarisation | Solarization of grid connected pumping installation Kasanda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. |  |  | ORD/002049/2022-2023 | 968/W/MMD | 29/03/2023 | 25/09/2023 | RSA ENTERPRISE | 6.25 | 5.15 | 82.46 | 80
2 | PASCHIM MEDINIPUR |  | Jhargram Mechanical Division | Solarization of grid connected pumping installation Kasanda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17733 | Solarisation | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Chaita and adjacent water supply schemes for JJM works under Jhargram Mechanical Division, P.H.E. Dte. | Driller-In-Charge | Junior Engineer | ORD/000725/2024-2025 | 6881/JMD | 05/09/2024 | 05/10/2024 | MUKHERJEE ART CENTRE | 3.01 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR |  | Jhargram Mechanical Division | Solarization of grid connected pumping installation Kasanda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17733 | Solarisation | Quotation for SOLAR PANEL connection at KASANDA TW -I water supply. |  |  | BILL/00323/2024-2025 | 142/JMD | 24/05/2024 | 24/05/2024 | WBSEDCL | 0.2 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Jhargram Mechanical Division | Solarization of grid connected pumping installation Kasanda PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17733 | Solarisation | Application Fee for Solar Power Plant at Kasanda T/W - I water supply scheme. |  |  | BILL/01365/2023-2024 | 28/JMD | 11/03/2024 | 11/03/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
Total | [13 empty] | 9.46 | 5.15 | 54.44