## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation Shanrpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17737 | Solarisation | Solarization of grid connected pumping installation Shanrpur PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002056/2022-2023 | 972/W/MMD | 29/03/2023 | 25/09/2023 | RSA ENTERPRISE | 6.25 | 4.87 | 78.03 | 70
Total | [13 empty] | 6.25 | 4.87 | 78.03