## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation Hatimasan PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17738 | Solarisation | Solarization of grid connected pumping installation Hatimasan PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002081/2022-2023 | 988/W/MMD | 29/03/2023 | 25/09/2023 | BHABANI PRASAD MANNA | 6.26 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Jhargram Mechanical Division | Solarization of grid connected pumping installation Hatimasan PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17738 | Solarisation | Processing Fee for Net Meter installation for solar power plant at Hatimasan pump house 1,Block :- Garbeta 2. SCHEME CODE :- SM/17738 |  |  | BILL/01677/2024-2025 | 471/JMD | 30/01/2025 | 30/01/2025 | WBSEDCL | 0.01 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Jhargram Mechanical Division | Solarization of grid connected pumping installation Hatimasan PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17738 | Solarisation | Quotation for meter installation for solar power plant at Hatimasan :- 1. (SM/17738) |  |  | BILL/00919/2025-2026 |  | 22/08/2025 | 22/08/2025 | WBSEDCL | 0.55 | 0 | 0 | 0
Total | [13 empty] | 6.81 | 0 | 0