## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation Amlagora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17739 | Solarisation | Solarization of grid connected pumping installation Amlagora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. |  |  | ORD/002058/2022-2023 | 973/W/MMD | 29/03/2023 | 25/09/2023 | RSA ENTERPRISE | 6.25 | 6.25 | 100 | 100
2 | PASCHIM MEDINIPUR |  | Jhargram Mechanical Division | Solarization of grid connected pumping installation Amlagora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17739 | Solarisation | New Service connection charges. |  |  | BILL/01403/2023-2024 | 66/JMD | 13/03/2024 | 13/03/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Jhargram Mechanical Division | Solarization of grid connected pumping installation Amlagora PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17739 | Solarisation | solar quotation charges at Amlagora water supply scheme |  |  | BILL/00021/2024-2025 | 20/JMD | 15/04/2024 | 15/04/2024 | WBSEDCL | 0.31 | 0 | 0 | 0
Total | [13 empty] | 6.56 | 6.25 | 95.15