## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Ukhla PWSS in the District of Paschim Medinipur under JJM programme. | SM/17755 | Augmentation | Electric quotation bill for load enhacement at Tw no-I of Ukhla water supply scheme. Consumer ID-200331903. |  |  | BILL/00267/2023-2024 |  | 22/05/2023 | 22/05/2023 | WBSEDCL | 0.36 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Ukhla PWSS in the District of Paschim Medinipur under JJM programme. | SM/17755 | Augmentation | Rejuvenation of Electro-Mechanical components of Ukhla PWSS in the District of Paschim Medinipur under JJM programme under MMD PHE Dte. |  |  | ORD/002123/2022-2023 | 1061/W/MMD | 29/03/2023 | 25/09/2023 | ABHIJIT MUKHERJEE | 21.09 | 0 | 0 | 55
3 | PASCHIM MEDINIPUR |  | Jhargram Mechanical Division | Rejuvenation of Electro-Mechanical components of Ukhla PWSS in the District of Paschim Medinipur under JJM programme. | SM/17755 | Augmentation | Repairing & rejuvenation of electro-mechanical accessories for Ukhla W/S scheme Pump house no -2 in Garbeta II block under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000794/2024-2025 | 7246/JMD | 05/11/2024 | 12/05/2025 | ABHIJIT MUKHERJEE | 4.43 | 0 | 0 | 100
Total | [13 empty] | 25.88 | 0 | 0