## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation Dhaneswarpur (Dantan-II) PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17765 | Solarisation | Solarization of grid connected pumping installation Dhaneswarpur (Dantan-II) PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002072/2022-2023 | 982/W/MMD | 29/03/2023 | 25/09/2023 | BHABANI PRASAD MANNA | 6.26 | 4.89 | 78.03 | 80
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Solarization of grid connected pumping installation Dhaneswarpur (Dantan-II) PWSS in Paschim Medinipore District under JJM programme under Midnapore Mechanical Division, PHE Dte. | SM/17765 | Solarisation | Quotation for Application fee of Solar Power Plant 10 KW at PH-I of Dhaneshwarpur PWSS .Application No-2004583657, Ref Consumer ID-212392694,Biiling Type-NET BILLING, NAME OF CCC-KHAKURDA CCC, SCHEME CODE-SM/17765, BLOCK-DANTAN-II |  |  | BILL/03618/2023-2024 | BP-2023-24-650 | 09/02/2024 | 09/02/2024 | WBSEDCL | 0.01 | 0 | 0 | 0
Total | [13 empty] | 6.27 | 4.89 | 77.95