## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Electro-Mechanical components of Chotokalshibhanga PWSS in the District of Paschim Medinipur under JJM programme. | SM/17796 | Augmentation | Rejuvenation of Electro-Mechanical components of Chotokalshibhanga PWSS in the District of Paschim Medinipur under JJM programme under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002124/2022-2023 | 1062/W/MMD | 29/03/2023 | 25/09/2023 | THE GODFATHER TRADING COMPANY | 5.07 | 5.07 | 100 | 60
Total | [13 empty] | 5.07 | 5.07 | 100